## Summary
| 2015 | 2016 | 2018 | 2020 | total
Project_# | 14 | 15 | 28 | 17 | 74
TIRCP_Award_Amount_($) | 224328000 | 788444000 | 4251722000 | 500000000 | 5764494000
Allocated_Amount | 224278000 | 422477816 | 1627802000 | 74030000 | 2348587816
Expended_Amount | 143556084.9 | 119517737.55 | 210456649.72 | 1823462.51 | 475353934.68
Expended_Percent_of_Awarded | 0.63994 | 0.15159 | 0.049499 | 0.0036469 | 0.082462
Expended_Percent_of_Allocated | 0.64008 | 0.2829 | 0.12929 | 0.024631 | 0.2024
Percent_Allocated | 0.99978 | 0.53584 | 0.38286 | 0.14806 | 0.40742

## FY
Award_Year | Award_Recipient | Implementing_Agency | Project_Title | Phase | Components | PPNO | Allocation_Date | Third_Party_Award_Date | Completion_Date | Phase_Completion_Date | Percent_of_Award_Fully_Allocated | TIRCP_Award_Amount | Allocation_Allocation_Sheet | GGRF_Funding | Expended_Amount | PTA-SB1 Allocation Amount | Allocated_Before_July_2020_1_is_yes | Percent_of_Allocation_Expended
2015 | Antelope Valley Transit Authority | Antelope Valley Transit Authority | Regional Transit Interconnectivity & Environmental Sustability | CONST | Purchase 13 60-foot articulated BRT buses and 16 45-foot electric commuter buses | CP005 | 2015-10-22 | 2016-03-14 | 2022-03-30 | 2022-03-31 | 1 | 24403000 | 24403000 | 24403000 | 21714177.53 | 0 | 1 | 0.88982
| Capitol Corridor Joint Powers Authority | Capitol Corridor Joint Powers Authority | Travel Time Reduction Project | CONST | Track and curve improvements between San Jose and Martinez for faster journeys benefiting Capitol Corridor passengers | CP012 | 2016-05-19 | 2016-06-01 | 2019-06-01 | 2019-06-01 | 1 | 4620000 | 4620000 | 4620000 | 4619999.9 | 0 | 1 | 1
| Los Angeles County Metropolitan Transportation Authority | Los Angeles County Metropolitan Transportation Authority | Willowbrook/Rosa Parks Station & Blue Line Light Rail Operational Improvements Project | CONST | Replace Blue Line signal system; install new track crossovers, new train controls at 15 locations, new LED signals and power switches, 19 turnouts, new track, overhead catenary, and a communications upgrade. | CP015 | 2016-06-30 | 2017-06-28 | 2021-06-30 | 2020-06-28 | 1 | 38494000 | 38494000 | 38494000 | 38494000 | 0 | 1 | 1
| Los Angeles-San Diego-San Luis Obispo Rail Corridor Agency (LOSSAN) | Los Angeles-San Diego-San Luis Obispo Rail Corridor Agency (LOSSAN) | Pacific Surfliner Transit Transfer Program | CONST | LOSSAN and 12 transit agencies from San Luis Obispo to San Diego counties to use seamless ticketing to increase use of transit | CP007 | 2015-12-10 | 2016-06-01 | 2021-06-30 | 2021-06-30 | 1 | 1675000 | 1675000 | 1675000 | 277840.47 | 0 | 1 | 0.16587
| Monterey-Salinas Transit | Monterey-Salinas Transit | Monterey Bay Operations and Maintenance Facility/Salinas Transit Service Project | CONST | Renovation and expansion of the Monterey maintenance and operations facility. | CP013 | 2016-05-19 | 2016-11-03 | 2018-09-30 | 2019-11-03 | 1 | 10000000 | 10000000 | 10000000 | 0 | 0 | 1 | 0
| Orange County Transportation Authority (OCTA) | Orange County Transportation Authority (OCTA) | Bravo! Route 560 Rapid Buses | CONST | Purchase five 40-foot CNG buses for BRT Route linking SARTC to Metrolink/Amtrak | CP004 | 2015-10-22 | 2015-11-30 | 2018-02-11 | 2018-11-30 | 1 | 2320000 | 2320000 | 2320000 | 0 | 0 | 1 | 0
| Sacramento Regional Transit District | Sacramento Regional Transit District | Sacramento Regional Transit's Refurbishment of 7 Light Rail Vehicles | CONST | Refurbishment of Seven UTDC Light Rail Vehicles Used Throughout the System | CP001 | 2015-08-27 | 2015-10-21 | 2020-06-30 | 2020-06-30 | 1 | 6427000 | 6427000 | 6427000 | 0 | 0 | 1 | 0
| San Diego Association of Governments (SANDAG) | San Diego Association of Governments (SANDAG) | South Bay Bus Rapid Transit | CONST | Bus Rapid Transit Route between Downtown San Diego and the Otay Mesa Crossing | CP003 | 2015-08-27 | 2016-01-08 | 2020-09-30 | 2019-01-08 | 1 | 4000000 | 4000000 | 4000000 | 4000000 | 0 | 1 | 1
| San Diego Metropolitan Transit System (MTS) | San Diego Metropolitan Transit System (MTS) | San Diego Metropolitan Transit System Trolley Capacity Improvements | CONST | Courthouse Trolley Station (Construction) | CP008 | 2017-06-29 | 2017-05-30 | 2020-06-29 | 2020-06-29 | 0 | 0 | 3760000 | 3760000 | 28176000 | 0 | 1 | 7.4936
[5 empty] | Purchase 8 trolley vehicles to expand service on the Blue and Orange lines | CP008 | 2016-10-20 | 2016-11-01 | 2019-11-01 | 2019-11-01 | 0 | 0 | 27463000 | 27463000 | 28176000 | 0 | 1 | 1.026
|  |  |  | PS&E | Courthouse Trolley Station (Design) | CP008 | 2016-01-21 | 2000-01-01 | 2018-06-30 | 2018-06-30 | 0.99844 | 31986000 | 713000 | 713000 | 28176000 | 0 | 1 | 39.5175
| San Francisco Municipal Transportation Agency | San Francisco Municipal Transportation Agency | SFMTA Light Rail Vehicle Fleet Expansion | CONST | Purchase 8 Zero-emission Light Rail Vehicles for MUNI Service Expansion | CP006 | 2015-12-10 | 2015-01-01 | 2018-12-10 | 2018-12-10 | 1 | 41181000 | 41181000 | 41181000 | 0 | 0 | 1 | 0
| San Joaquin Regional Rail Commission | San Joaquin Regional Rail Commission | ACE Wayside Power Project | CONST | Installation of wayside power sources at ACE’s new Regional Maintenance Facility in Stockton | CP014 | 2018-01-31 | 2018-02-02 | 2019-11-13 | 2021-02-02 | 0 | 0 | 185000 | 185000 | 200000 | 0 | 1 | 1.0811
|  |  |  | PS&E | Installation of wayside power sources at ACE’s new Regional Maintenance Facility in Stockton | CP014 | 2017-08-17 | 2000-01-01 | 2019-11-13 | 2020-06-30 | 1 | 200000 | 15000 | 15000 | 200000 | 0 | 1 | 13.3333
| San Joaquin Regional Transit District | San Joaquin Regional Transit District | Bus Rapid Transit – Martin Luther King Corridor and Crosstown Miner Corridor | CONST | Bus rapid transit infrastructure along the MLK Corridor and Crosstown Miner Corridor, including the acquisition of 12 new zero-emission electric vehicles | CP011 | 2017-01-19 | 2017-06-23 | 2020-03-30 | 2020-06-23 | 1 | 6841000 | 6841000 | 6841000 | 6841000 | 0 | 1 | 1
| Sonoma-Marin Area Rail Transit District | Sonoma-Marin Area Rail Transit District | SMART Rail Car Capacity Project | CONST | Purchase four rail cars, two "A"cars and two "B" cars, for expansion of SMART's fleet | CP010 | 2016-03-17 | 2016-04-06 | 2021-12-30 | 2000-01-01 | 1 | 11000000 | 11000000 | 11000000 | 1650000 | 0 | 1 | 0.15
| Southern California Regional Rail Authority (Metrolink) | Southern California Regional Rail Authority (Metrolink) | Purchase of Nine Fuel-Efficient Tier IV EMD F-125 Locomotives | CONST | Purchase nine of 20 locomotives that complete Metrolink's replacement program and expand service with three locomotives. | CP002 | 2016-03-17 | 2015-10-15 | 2022-09-30 | 2021-09-30 | 1 | 41181000 | 41181000 | 41181000 | 37583067 | 0 | 1 | 0.91263
2016 | Antelope Valley Transit Authority | SunLine Transit Agency | Zero Emission Bus and Vanpool Expansion in the Antelope Valley, Kern County and the Coachella Valley | CONST | Purchase 4 zero-emission buses to be operated by SunLine Transit within Coachella Valley | CP019 | 2017-01-19 | 2017-05-16 | 2000-01-01 | 2020-05-16 | 1.3779 | 6481000 | 2449000 | 2449000 | 7874722.49 | 0 | 1 | 3.2155
| Capitol Corridor Joint Powers Authority | Capitol Corridor Joint Powers Authority | Increased Rail Service to Roseville, Service Optimization and Standby Power Investments | CONST | Install 2 Standby Power Cabinets | CP023 | 2017-03-16 | 2019-01-09 | 2024-06-30 | 2021-01-09 | 0.38293 | 8999000 | 200000 | 200000 | 532908.06 | 0 | 1 | 2.6645
[5 empty] | Optimization Study | CP023 | 2017-05-17 | 2017-06-01 | 2021-06-30 | 2020-05-23 | 0 | 0 | 320000 | 320000 | 532908.06 | 0 | 1 | 1.6653
[10 empty] | 2021-06-30 | 0 | 0 | 0 | 0 | 532908.06 | 0 | 1 | inf
[5 empty] | Sacramento to Roseville 3rd Mainline Track | CP023 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 0 | 0 | 0 | 0 | 532908.06 | 0 | 1 | inf
|  |  |  | PS&E | Sacramento to Roseville 3rd Mainline Track | CP023 | 2017-06-29 | 2000-01-01 | 2000-01-01 | 2019-06-30 | 0 | 0 | 886000 | 886000 | 532908.06 | 0 | 1 | 0.60148
[10 empty] | 2021-02-28 | 0 | 0 | 0 | 0 | 532908.06 | 0 | 1 | inf
[10 empty] | 2024-02-28 | 0 | 0 | 0 | 0 | 532908.06 | 0 | 1 | inf
[7 empty] | 2018-08-16 | 2000-01-01 | 2000-01-01 | 2021-02-28 | 0 | 0 | 2000000 | 2000000 | 532908.06 | 0 | 1 | 0.26645
[10 empty] | 2024-02-28 | 0 | 0 | 0 | 0 | 532908.06 | 0 | 1 | inf
|  |  |  | R/W | Sacramento to Roseville 3rd Mainline Track | CP023 | 2017-06-29 | 2000-01-01 | 2000-01-01 | 2019-06-30 | 0 | 0 | 40000 | 40000 | 532908.06 | 0 | 1 | 13.3227
[10 empty] | 2021-02-28 | 0 | 0 | 0 | 0 | 532908.06 | 0 | 1 | inf
[10 empty] | 2024-02-28 | 0 | 0 | 0 | 0 | 532908.06 | 0 | 1 | inf
| City of Fresno | City of Fresno | Metropolitan Rapid Transit and Rail Connectivity Project | CONST | Bus Stop Improvements | CP016 | 2020-06-25 | 2000-01-01 | 2024-06-24 | 2023-06-25 | 0 | 0 | 3917000 | 3917000 | 0 | 0 | 1 | 0
[5 empty] | Modernize Fare Payment Systems | CP016 | 2016-12-08 | 2017-01-13 | 2022-12-30 | 2022-12-30 | 1 | 8000000 | 4083000 | 4083000 | 0 | 0 | 1 | 0
| Foothill Transit | Foothill Transit | Transforming California: Bus Electrification, Service Expansion and Rail Integration | CONST | Purchase 20 zero-emission electric buses to extend Route 486 to Pomona Metrolink Station and increase frequencies | CP076 | 2021-06-24 | 2000-01-01 | 2024-06-01 | 2024-06-24 | 1 | 5000000 | 5000000 | 5000000 | 0 | 0 | 0 | 0
| Los Angeles County Metropolitan Transportation Authority | Los Angeles County Metropolitan Transportation Authority | Airport Metro Connector 96th Street Station/Metro Green Line Extension to LAX | CONST | Construct New Station to Connect LAX People Mover to Metro Green Line, Crenshaw Line and Buses | CP058 | 2020-06-25 | 2000-01-01 | 2025-07-30 | 2024-07-31 | 1 | 40000000 | 40000000 | 40000000 | 0 | 0 | 1 | 0
|  |  | Metro Red Line and Purple Line Core Capacity Improvements | CONST | Construction | CP020 | 2019-12-05 | 2020-03-26 | 2024-07-25 | 2024-07-31 | 0 | 0 | 64437000 | 64437000 | 4220881.34 | 0 | 1 | 0.065504
|  |  |  | PA&ED | Environmental assessment | CP020 | 2017-01-19 | 2000-01-01 | 2022-06-30 | 2019-06-30 | 1.0034 | 69209000 | 1908000 | 1908000 | 4220881.34 | 0 | 1 | 2.2122
|  |  |  | PS&E | Final design | CP020 | 2017-06-29 | 2000-01-01 | 2019-05-21 | 2000-01-01 | 0 | 0 | 3101000 | 3101000 | 4220881.34 | 0 | 1 | 1.3611
| Los Angeles-San Diego-San Luis Obispo Rail Corridor Agency (LOSSAN) | San Diego Association of Governments (SANDAG) | All Aboard: Transforming Southern California Rail Travel | CONST | Elvira to Morena Double Track | CP021 | 2017-03-16 | 2017-02-28 | 2022-10-31 | 2020-03-16 | 0.90805 | 82000000 | 49995000 | 49995000 | 66831938.8 | 0 | 1 | 1.3368
[7 empty] | 2018-02-01 | 2017-02-28 | 2022-10-31 | 2000-01-01 | 0 | 0 | 11988000 | 11988000 | 66831938.8 | 0 | 1 | 5.5749
| Orange County Transportation Authority (OCTA) | Orange County Transportation Authority (OCTA) | OC Streetcar and OCTA System-Wide Mobile Ticketing | CONST | Mobile ticketing implementation on fixed route bus system | CP017 | 2016-10-20 | 2016-11-21 | 2018-02-01 | 2019-11-21 | 1 | 28000000 | 2482000 | 2482000 | 0 | 0 | 1 | 0
[5 empty] | New line connecting SARTC with new multimodal hub at Harbor Blvd, 8 LRVs | CP017 | 2018-05-17 | 2018-11-19 | 2022-10-31 | 2021-02-28 | 0 | 0 | 25518000 | 25518000 | 0 | 0 | 1 | 0
| Peninsula Corridor Joint Powers Board | Peninsula Corridor Joint Powers Board | Peninsula Corridor Electrification Project | CONST | Electrify Caltrain Corridor and Procurement of electric multiple unit vehicles | CP022 | 2017-06-29 | 2016-08-15 | 2022-08-22 | 2022-08-22 | 1 | 20000000 | 20000000 | 20000000 | 14102518.86 | 0 | 1 | 0.70513
| Sacramento Regional Transit District | Sacramento Regional Transit District | Downtown/Riverfront Sacramento-West Sacramento Streetcar | CONST | Construct new streetcar line linking Sacramento and West Sacramento | CP080 | 2026-12-31 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 0 | 30000000 | 0 | 0 | 0 | 0 | 0
| San Bernardino County Transportation Authority (SBCTA) | San Bernardino County Transportation Authority (SBCTA) | Redlands Passenger Rail Project | CONST | Construct new Rail System linking San Bernardino and the University of Redlands | 1230 | 2018-10-18 | 2019-05-15 | 2022-07-31 | 2022-06-01 | 1 | 9204000 | 9204000 | 9204000 | 9204000 | 0 | 1 | 1
| San Francisco Municipal Transportation Agency | San Francisco Municipal Transportation Agency | Light Rail Modernization and Expansion Program | CONST | Purchase 10 Expansion Light Rail Vehicles to Increase Capacity and Improve Service | CP006 | 2017-05-18 | 2015-01-01 | 2020-05-07 | 2000-01-01 | 0 | 0 | 45092000 | 45092000 | 0 | 0 | 1 | 0
| San Joaquin Regional Rail Commission | San Joaquin Regional Rail Commission | ACE Near-Term Capacity Improvement Program | CONST | Platforms (Construction) | CP025 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 1
[5 empty] | Procurement of Tier IV Locomotives | CP025 | 2017-08-17 | 2018-04-20 | 2021-04-20 | 2021-04-20 | 0 | 0 | 7500000 | 7500000 | 0 | 0 | 1 | 0
|  |  |  | PA&ED | Platforms (PA&ED-exempt) | CP025 | 2018-06-28 | 2000-01-01 | 2000-01-01 | 2020-06-30 | 0.48606 | 16459000 | 0 | 0 | 0 | 0 | 1
|  |  |  | PS&E | Platforms (PS&E) | CP025 | 2018-06-28 | 2000-01-01 | 2022-01-01 | 2020-06-30 | 0 | 0 | 500000 | 500000 | 0 | 0 | 1 | 0
|  |  | SB 132 ACE Extension Lathrop to Ceres/Merced | CONST | Procurement of Two Tier IV locomotives | CP026 | 2000-01-01 | 2020-02-07 | 2027-12-01 | 2000-01-01 | 0 | 0 | 14698284 | 0 | 16750768 | 0 | 1 | 1.1396
[5 empty] | Procurement of bi-level cab cars | CP026 | 2000-01-01 | 2020-02-07 | 2027-12-01 | 2000-01-01 | 0 | 0 | 19000000 | 0 | 16750768 | 0 | 1 | 0.88162
[5 empty] | Working Capital | CP026 | 2000-01-01 | 2020-02-07 | 2027-12-01 | 2000-01-01 | 0 | 0 | 13290000 | 0 | 16750768 | 0 | 1 | 1.2604
|  |  |  | PA&ED | PA&ED Consulting Services | CP026 | 2000-01-01 | 2020-02-07 | 2027-12-01 | 2000-01-01 | 0.25725 | 400000000 | 16752568 | 0 | 16750768 | 0 | 1 | 0.99989
|  |  |  | PS&E | PS&E for Stations, track work, and layover facilities | CP026 | 2000-01-01 | 2020-02-07 | 2027-12-01 | 2000-01-01 | 0 | 0 | 34006667 | 0 | 16750768 | 0 | 1 | 0.49257
|  |  |  | ROW | ROW for Stations and layover facilities | CP026 | 2000-01-01 | 2020-02-07 | 2027-12-01 | 2000-01-01 | 0 | 0 | 5152297 | 0 | 16750768 | 0 | 1 | 3.2511
| Santa Clara Valley Transportation Authority | Santa Clara Valley Transportation Authority | BART Silicon Valley Phase II Extension | CONST | Procurement of BART Vehicles for BART to San Jose Extension | CP057 | 2000-01-01 | 2023-12-30 | 2030-06-01 | 2000-01-01 | 0 | 20000000 | 0 | 0 | 0 | 0 | 1
2018 | Alameda Contra Costa Transit District | Alameda Contra Costa Transit District | Purchase Zero Emission High Capacity Buses to Support Transbay Tomorrow and Clean Corridors Plan | CONST | Facilities and bus charging infrastructure | 2320B | 2000-01-01 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 0 | 0 | 0 | 0 | 500000 | 0 | 1 | inf
[5 empty] | Network Integration | 2320B | 2018-10-18 | 2019-04-19 | 2020-06-30 | 2000-01-01 | 0 | 0 | 500000 | 0 | 500000 | 500000 | 1 | 1
[5 empty] | Zero-Emission Buses for Service Expansion | 2320B | 2020-10-22 | 2020-11-01 | 2024-04-01 | 2000-01-01 | 0.57143 | 14000000 | 6500000 | 2988000 | 500000 | 3512000 | 0 | 0.076923
|  |  |  | PS&E | Facilities and bus charging infrastructure | 2320B | 2020-10-22 | 2020-11-01 | 2021-10-01 | 2000-01-01 | 0 | 0 | 1000000 | 459000 | 500000 | 541000 | 0 | 0.5
| Anaheim Transportation Network (ATN) | Anaheim Transportation Network (ATN) | #Electrify Anaheim: Changing the Transit Paradigm in Southern California | CONST | 10 Micro transit Electric Vehicles, Signage & Mobile App Development | CP027 | 2018-08-16 | 2019-02-13 | 2020-06-30 | 2020-06-30 | 1 | 28617000 | 802000 | 355000 | 15829360.48 | 447000 | 1 | 19.7374
[5 empty] | 40 Zero-Emission Electric Buses | CP027 | 2018-12-06 | 2019-07-23 | 2023-06-30 | 2023-06-30 | 0 | 0 | 22857000 | 10134000 | 15829360.48 | 12723000 | 1 | 0.69254
[5 empty] | Construction of New O&M facility with Solar Canopy to Charge Zero-Emission Vehicles | CP027 | 2019-10-09 | 2020-04-03 | 2023-04-03 | 2021-06-01 | 0 | 0 | 4958000 | 2198000 | 15829360.48 | 2760000 | 1 | 3.1927
| Antelope Valley Transit Authority & Long Beach Transit | Antelope Valley Transit Authority | From the Desert to the Sea: Antelope Valley Transit Authority and Long Beach Transit Zero Emission Bus Initiative | CONST | 7 Zero-Emission Electric Buses and Upgrades to Supporting Infrastructure | CP028 | 2018-10-18 | 2019-07-02 | 2021-07-31 | 2021-07-31 | 1 | 9205000 | 7755000 | 3505000 | 2641815.25 | 4250000 | 1 | 0.34066
[5 empty] | Facility Improvements | CP028 | 2020-05-14 | 2020-07-13 | 2023-07-13 | 2023-07-13 | 0 | 0 | 1200000 | 542000 | 2641815.25 | 658000 | 1 | 2.2015
[5 empty] | Network Integration | CP028 | 2018-10-18 | 2019-01-07 | 2022-01-07 | 2022-01-07 | 0 | 0 | 250000 | 0 | 2641815.25 | 250000 | 1 | 10.5673
| Bay Area Rapid Transit District | Bay Area Rapid Transit District | The Transbay Corridor Core Capacity Program: Vehicle Acquistion and Communications-Based Train Control System | CONST | New BART Rail Vehicles and Communication-Based Train Control System for Improved Service(Acquisition of 272 new rail vehicles and communication- based train control systems to allow for increase service frequency) | CP055 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 0 | 0 | 50000000 | 0 | 0 | 50000000 | 1 | 0
[7 empty] | 2019-12-05 | 2020-09-16 | 2030-01-01 | 2030-12-30 | 1.1569 | 318600000 | 51492000 | 22831000 | 0 | 28661000 | 1 | 0
[7 empty] | 2021-05-14 | 2020-09-16 | 2030-01-01 | 2030-12-30 | 0 | 0 | 267108000 | 118436000 | 0 | 148672000 | 0 | 0
| Capitol Corridor Joint Powers Authority | Capitol Corridor Joint Powers Authority | The Northern California Corridor Enhancement Program | CONST | Integrated Travel Program for Statewide Service and Ticket Integration | CP036 | 2018-08-16 | 2000-01-01 | 2021-12-25 | 2019-02-15 | 0 | 0 | 6000000 | 2660000 | 29586486.45 | 3340000 | 1 | 4.9311
[7 empty] | 2018-12-06 | 2000-01-01 | 2021-12-25 | 2019-02-15 | 0 | 0 | 0 | 68000 | 29586486.45 | -68000 | 1 | inf
[8 empty] | 2019-01-18 | 2021-12-25 | 2023-12-31 | 0 | 0 | 0 | 0 | 29586486.45 | 0 | 1 | inf
[5 empty] | Integrated Travel Program for Statewide Service and Ticket Integration (Ph 3b & 4) | CP036 | 2020-05-14 | 2020-05-14 | 2021-12-25 | 2024-12-31 | 0 | 0 | 21340000 | 9702000 | 29586486.45 | 11638000 | 1 | 1.3864
[5 empty] | Network Integration | CP036 | 2018-12-06 | 2019-03-27 | 2020-11-30 | 2020-11-30 | 0 | 0 | 2000000 | 0 | 29586486.45 | 2000000 | 1 | 14.7932
[9 empty] | 2021-12-23 | 2023-12-31 | 0 | 0 | 0 | 0 | 29586486.45 | 0 | 1 | inf
[5 empty] | South Bay Connector Project | CP036 | 2000-01-01 | 2000-01-01 | 2021-12-26 | 2000-01-01 | 0 | 0 | 0 | 0 | 29586486.45 | 0 | 1 | inf
|  |  |  | PA&ED | South Bay Connector Project | CP036 | 2018-08-16 | 2000-01-01 | 2022-02-16 | 2021-06-30 | 0 | 0 | 3120000 | 1418000 | 29586486.45 | 1702000 | 1 | 9.4828
[7 empty] | 2018-12-06 | 2000-01-01 | 2022-02-16 | 2021-06-30 | 0.62285 | 80340000 | 80000 | 37000 | 29586486.45 | 43000 | 1 | 369.8311
[7 empty] | 2020-05-14 | 2000-01-01 | 2000-01-01 | 2023-06-30 | 0 | 0 | 17500000 | 7956000 | 29586486.45 | 9544000 | 1 | 1.6907
| City of Fresno | City of Fresno | Southwest Fresno Community Connector | CONST | Purchase 6 long-range electric buses | CP079 | 2020-06-25 | 2020-12-16 | 2023-06-25 | 2023-06-25 | 0 | 0 | 7555000 | 3349000 | 0 | 4206000 | 1 | 0
|  |  |  | PS&E | Supporting Infrastructure for Buses | CP079 | 2020-06-25 | 2000-01-01 | 2022-06-30 | 2022-06-30 | 1 | 7798000 | 243000 | 107000 | 0 | 136000 | 1 | 0
| City of Los Angeles | City of Los Angeles | Los Angeles City: Leading the Transformation to Zero-Emission Electric Bus Transit Service | CONST | Network Integration | CP029 | 2018-08-16 | 2018-08-16 | 2022-10-01 | 2019-12-31 | 0 | 0 | 250000 | 0 | 0 | 250000 | 1 | 0
[5 empty] | Zero-Emission Electric Buses, Supporting Infrastructure, and Facility Upgrades | CP029 | 2018-08-16 | 2019-10-25 | 2022-10-01 | 2019-12-31 | 1 | 36104000 | 35854000 | 16008000 | 0 | 19846000 | 1 | 0
| City of Santa Monica | City of Santa Monica | Electric Blue: Electrification of City of Santa Monica's Big Blue Bus | CONST | 10 Zero-Emission Electric Buses | CP054 | 2019-06-27 | 2020-02-03 | 2023-02-03 | 2023-02-03 | 1 | 3050000 | 3050000 | 1352000 | 0 | 1698000 | 1 | 0
| Livermore Amador Valley Transit Authority | Livermore Amador Valley Transit Authority | Dublin/Pleasanton Capacity Improvement and Congestion Reduction Program | CONST | Multi-level Parking Structure | CP051 | 2019-10-09 | 2020-12-08 | 2022-02-08 | 2022-11-30 | 1 | 20500000 | 20000000 | 9089000 | 157092.4 | 10911000 | 1 | 0.0078546
[5 empty] | Network Integration | CP051 | 2018-12-06 | 2019-06-03 | 2021-12-31 | 2021-06-16 | 0 | 0 | 500000 | 0 | 157092.4 | 500000 | 1 | 0.31418
| Los Angeles County Metropolitan Transportation Authority | Los Angeles County Metropolitan Transportation Authority | Los Angeles Region Transit System Integration and Modernization Program of Projects | CONST | East San Fernando Valley Transit Corridor | CP030 | 2000-01-01 | 2022-12-31 | 2029-06-01 | 2000-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 1
[5 empty] | Gold Line Foothill Light Rail Extension Azusa to Pomona | CP030 | 2020-06-25 | 2019-08-14 | 2025-01-31 | 2000-01-01 | 0.23996 | 1088499000 | 249200000 | 111218000 | 0 | 137982000 | 1 | 0
[5 empty] | Gold Line Foothill Light Rail Extension Pomona to Montclair | CP030 | 2000-01-01 | 2025-12-31 | 2025-01-01 | 2000-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 1
[5 empty] | Green Line Light Rail Extension to Torrance | CP030 | 2000-01-01 | 2025-12-31 | 2031-06-30 | 2000-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 1
[5 empty] | Network Integration | CP030 | 2018-12-06 | 2020-02-27 | 2023-11-30 | 2000-01-01 | 0 | 0 | 7000000 | 0 | 0 | 7000000 | 1 | 0
[5 empty] | Orange/Red Line to Gold Line BRT Connector | CP030 | 2000-01-01 | 2023-12-31 | 2026-01-01 | 2000-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 1
[5 empty] | West Santa Ana Light Rail Transit Corridor | CP030 | 2000-01-01 | 2024-12-31 | 2030-06-30 | 2000-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  |  |  | PA&ED | Vermont Transit Corridor | CP030 | 2021-03-13 | 2022-06-30 | 2029-06-01 | 2000-01-01 | 0 | 0 | 5000000 | 2231000 | 0 | 2769000 | 0 | 0
| Los Angeles-San Diego-San Luis Obispo Rail Corridor Agency (LOSSAN) | Los Angeles-San Diego-San Luis Obispo Rail Corridor Agency (LOSSAN) | All Aboard 2018: Transforming SoCal Rail Travel | CONST | Network Integration | CP031 | 2000-01-01 | 2021-12-01 | 2023-12-01 | 2000-01-01 | 0 | 0 | 0 | 0 | 6381680.52 | 0 | 1 | inf
[5 empty] | On-Time Performance Incentive Program for Service Improvements NCTD | CP031 | 2018-12-06 | 2019-02-01 | 2019-11-12 | 2021-12-05 | 1.1132 | 22962000 | 2299000 | 1025000 | 6381680.52 | 1274000 | 1 | 2.7759
[7 empty] | 2019-10-09 | 2019-02-01 | 2022-10-09 | 2022-10-09 | 0 | 0 | 4367000 | 1949000 | 6381680.52 | 2418000 | 1 | 1.4613
[7 empty] | 2020-10-22 | 2000-01-01 | 2023-10-22 | 2000-01-01 | 0 | 0 | 16296000 | 7333000 | 6381680.52 | 8963000 | 0 | 0.39161
|  |  | Building Up: LOSSAN North Improvement Program | CONST | Network Integration | CP031 | 2000-01-01 | 2021-12-01 | 2023-12-01 | 2000-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 1
[5 empty] | On-Time Performance Incentive Program for Service Improvements NCTD | CP031 | 2018-12-06 | 2019-02-01 | 2019-11-12 | 2021-12-05 | 0 | 0 | 2299000 | 1025000 | 0 | 1274000 | 1 | 0
[7 empty] | 2019-10-09 | 2019-02-01 | 2022-10-09 | 2022-10-09 | 0 | 0 | 4367000 | 1949000 | 0 | 2418000 | 1 | 0
[7 empty] | 2020-10-22 | 2000-01-01 | 2023-10-22 | 2000-01-01 | 0 | 0 | 16296000 | 7333000 | 0 | 8963000 | 0 | 0
|  | North County Transit District (NCTD) | All Aboard 2018: Transforming SoCal Rail Travel | CONST | North San Diego County Fencing | CP031 | 2020-01-30 | 2021-01-21 | 2024-01-21 | 2024-01-21 | 0 | 0 | 1241000 | 554000 | 6381680.52 | 687000 | 1 | 5.1424
[5 empty] | OTC Pedestrian Crossing | CP031 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 0 | 0 | 0 | 0 | 6381680.52 | 0 | 1 | inf
[5 empty] | Signal Control Replacement - Carlsbad Crossings | CP031 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 0 | 0 | 0 | 0 | 6381680.52 | 0 | 1 | inf
[5 empty] | Signal Control Replacement - Encinitas & Del Mar | CP031 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 0 | 0 | 0 | 0 | 6381680.52 | 0 | 1 | inf
[5 empty] | Signal Control Replacement - Legacy Phase 2 | CP031 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 0 | 0 | 0 | 0 | 6381680.52 | 0 | 1 | inf
[5 empty] | Signal Control Replacement - San Diego Crossings | CP031 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 0 | 0 | 0 | 0 | 6381680.52 | 0 | 1 | inf
[5 empty] | Signal Train Control Replacement - Legacy Phase 1 | CP031 | 2021-06-25 | 2000-01-01 | 2000-01-01 | 2024-06-24 | 0 | 0 | 1100000 | 487000 | 6381680.52 | 613000 | 0 | 5.8015
[5 empty] | Signal optimization: BNSF Junction Control Point | CP031 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 0 | 0 | 0 | 0 | 6381680.52 | 0 | 1 | inf
|  |  |  | PS&E | North San Diego County Fencing | CP031 | 2018-10-18 | 2000-01-01 | 2021-06-30 | 2021-06-30 | 0 | 0 | 259000 | 115000 | 6381680.52 | 144000 | 1 | 24.6397
|  |  | Building Up: LOSSAN North Improvement Program | CONST | North San Diego County Fencing | CP031 | 2020-01-30 | 2021-01-21 | 2024-01-21 | 2024-01-21 | 0 | 0 | 1241000 | 554000 | 0 | 687000 | 1 | 0
[5 empty] | OTC Pedestrian Crossing | CP031 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 1
[5 empty] | Signal Control Replacement - Carlsbad Crossings | CP031 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 1
[5 empty] | Signal Control Replacement - Encinitas & Del Mar | CP031 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 1
[5 empty] | Signal Control Replacement - Legacy Phase 2 | CP031 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 1
[5 empty] | Signal Control Replacement - San Diego Crossings | CP031 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 1
[5 empty] | Signal Train Control Replacement - Legacy Phase 1 | CP031 | 2021-06-25 | 2000-01-01 | 2000-01-01 | 2024-06-24 | 0 | 0 | 1100000 | 487000 | 0 | 613000 | 0 | 0
[5 empty] | Signal optimization: BNSF Junction Control Point | CP031 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  |  |  | PS&E | North San Diego County Fencing | CP031 | 2018-10-18 | 2000-01-01 | 2021-06-30 | 2021-06-30 | 0 | 0 | 259000 | 115000 | 0 | 144000 | 1 | 0
| Peninsula Corridor Joint Powers Board | Peninsula Corridor Joint Powers Board | Peninsula Corridor Electrification Expansion Project | CONST | Bike Parking Enhancements | CP039 | 2021-01-28 | 2022-01-28 | 2023-06-30 | 2023-08-12 | 0 | 0 | 2975000 | 1343000 | 118882320.16 | 1632000 | 0 | 40.2991
[5 empty] | Corridor Wide Broadband Communications Network | CP039 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 0 | 0 | 0 | 0 | 59441160.08 | 0 | 1 | inf
[7 empty] | 2020-08-12 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 0 | 0 | 1475000 | 666000 | 59441160.08 | 809000 | 0 | 40.2991
[7 empty] | 2021-01-28 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 0 | 0 | -1475000 | -666000 | 59441160.08 | -809000 | 0 | -40.2991
[5 empty] | Network Integration | CP039 | 2018-08-15 | 2018-10-10 | 2000-01-01 | 2020-09-30 | 0 | 0 | 3000000 | 0 | 59441160.08 | 3000000 | 1 | 19.8137
[5 empty] | Procurement of 37 Electric Multiple Units (Multi-Year Funding) | CP039 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 0 | 0 | 0 | 0 | 59441160.08 | 0 | 1 | inf
[7 empty] | 2018-08-15 | 2024-12-31 | 2028-06-01 | 2000-01-01 | 0 | 0 | 31000000 | 14000000 | 59441160.08 | 17000000 | 1 | 1.9175
[7 empty] | 2019-06-27 | 2018-12-14 | 2022-11-30 | 2024-12-31 | 0 | 0 | 27000000 | 12195000 | 59441160.08 | 14805000 | 1 | 2.2015
[7 empty] | 2020-08-12 | 2018-12-14 | 2022-11-30 | 2024-12-31 | 0 | 0 | 59182000 | 26732000 | 59441160.08 | 32450000 | 0 | 1.0044
|  |  |  | PS&E | Bike Parking Enhancements | CP039 | 2021-01-28 | 2000-01-01 | 2021-01-29 | 2021-06-30 | 0 | 0 | 525000 | 237000 | 59441160.08 | 288000 | 0 | 113.2213
[5 empty] | Corridor Wide Broadband Communications Network | CP039 | 2018-10-18 | 2000-01-01 | 2021-04-30 | 2022-06-30 | 0.61718 | 203638000 | 3000000 | 1354000 | 59441160.08 | 1646000 | 1 | 19.8137
[7 empty] | 2020-08-12 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 0 | 0 | -1475000 | -666000 | 59441160.08 | -809000 | 0 | -40.2991
[7 empty] | 2021-01-28 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 0 | 0 | -525000 | -237000 | 59441160.08 | -288000 | 0 | -113.2213
[8 empty] | 2022-01-28 | 2021-04-30 | 2022-06-30 | 0 | 0 | 1000000 | 451000 | 59441160.08 | 549000 | 0 | 59.4412
| Sacramento Regional Transit District | Sacramento Regional Transit District | Accelerating Rail Modernization and Expansion in the Capital Region | CONST | Network Integration | CP053 | 2019-06-27 | 2019-06-27 | 2022-06-27 | 2021-11-30 | 0 | 0 | 250000 | 0 | 0 | 250000 | 1 | 0
[5 empty] | Purchase 20 Replacement and Expansion Low Floor LRVs | CP053 | 2019-12-05 | 2020-03-31 | 2026-02-12 | 2021-11-30 | 0.82645 | 64350000 | 30932000 | 13768000 | 0 | 17164000 | 1 | 0
[7 empty] | 2021-08-19 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 0 | 0 | 22000000 | 12208000 | 0 | 9792000 | 0 | 0
| San Bernardino County Transportation Authority (SBCTA) | San Bernardino County Transportation Authority (SBCTA) | Diesel Multiple Unit Vehicle to Zero- or Low-Emission Vehicle Conversion and West Valley Connector Bus Rapid Transit | CONST | ZEMU Supporting Infrastructure | CP034 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 0 | 0 | 0 | 0 | 20357085.98 | 0 | 1 | inf
[5 empty] | ZEMU Vehicle Procurement | CP034 | 2018-08-16 | 2019-11-13 | 2022-11-13 | 2024-06-01 | 0 | 0 | 12000000 | 5320000 | 20357085.98 | 6680000 | 1 | 1.6964
[7 empty] | 2019-12-05 | 2019-11-13 | 2022-11-13 | 2024-06-01 | 0 | 0 | 11500000 | 5099000 | 20357085.98 | 6401000 | 1 | 1.7702
|  |  |  | PA&ED | Supporting Infrastructure for Zero-Emission Vehicles | CP034 | 2018-08-16 | 2000-01-01 | 2021-06-30 | 2021-06-30 | 0.95 | 30000000 | 500000 | 221000 | 20357085.98 | 279000 | 1 | 40.7142
|  |  |  | PS&E | DMU to ZMU Conversion (Design) | CP034 | 2019-12-05 | 2000-01-01 | 2021-06-30 | 2021-06-30 | 0 | 0 | 4500000 | 1995000 | 20357085.98 | 2505000 | 1 | 4.5238
| San Diego Association of Governments (SANDAG) | San Diego Association of Governments (SANDAG) | Ride Between the Line: Enhancing Access to Transit in San Diego | CONST | Improvements to transit stops for improved services including separated bike lane along University Avenue | CP077 | 2000-01-01 | 2022-12-31 | 2025-06-01 | 2000-01-01 | 0 | 5763000 | 0 | 0 | 0 | 0 | 1
| San Diego Metropolitan Transit System (MTS) | San Diego Metropolitan Transit System (MTS) | Blue Line Rail Corridor Transit Enhancements | CONST | American Plaza Pedestrian Enhancements | CP032 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 1
[5 empty] | Beech Street Double Crossover | CP032 | 2020-12-03 | 2021-01-13 | 2024-01-13 | 2024-01-13 | 0 | 0 | 3691000 | 1646000 | 0 | 2045000 | 0 | 0
[5 empty] | Blue Line Feeder Bus Service (11 Buses) for Route 925 | CP032 | 2021-06-24 | 2000-01-01 | 2000-01-01 | 2021-06-24 | 0 | 0 | 13316000 | 5941000 | 0 | 7375000 | 0 | 0
[5 empty] | Blue Line Feeder Bus Service Charging Infrastructure for Route 925 | CP032 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 1
[5 empty] | Blue Line Feeder Bus Service Stop Improvements | CP032 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 1
[5 empty] | Green Line IMT Double Tracking | CP032 | 2020-12-03 | 2000-01-01 | 2024-12-31 | 2021-12-03 | 0 | 0 | 6354000 | 2835000 | 0 | 3519000 | 0 | 0
[5 empty] | Middletown Double Crossover | CP032 | 2019-10-09 | 2019-12-27 | 2022-12-27 | 2022-12-27 | 0 | 0 | 4977000 | 2220000 | 0 | 2757000 | 1 | 0
[5 empty] | Network Integration | CP032 | 2019-01-31 | 2019-06-13 | 2020-01-31 | 2020-01-31 | 0 | 0 | 250000 | 0 | 0 | 250000 | 1 | 0
[5 empty] | Old Town Transit Center Enhancements | CP032 | 2019-12-05 | 2020-08-11 | 2023-08-11 | 2023-08-11 | 0 | 0 | 2367000 | 1056000 | 0 | 1311000 | 1 | 0
|  |  |  | PS&E | American Plaza Pedestrian Enhancements | CP032 | 2019-03-14 | 2000-01-01 | 2021-06-30 | 2021-06-30 | 0 | 0 | 320000 | 142000 | 0 | 178000 | 1 | 0
[5 empty] | Beech Street Double Crossover | CP032 | 2019-03-14 | 2000-01-01 | 2021-06-30 | 2021-06-30 | 0.82004 | 40098000 | 360000 | 160000 | 0 | 200000 | 1 | 0
[5 empty] | Blue Line Feeder Bus Service Charging Infrastructure for Route 925 | CP032 | 2020-03-26 | 2000-01-01 | 2022-06-30 | 2000-01-01 | 0 | 0 | 372000 | 165000 | 0 | 207000 | 1 | 0
[5 empty] | Blue Line Feeder Bus Service Stop Improvements | CP032 | 2019-03-14 | 2000-01-01 | 2021-06-30 | 2021-06-30 | 0 | 0 | 240000 | 107000 | 0 | 133000 | 1 | 0
[5 empty] | Green Line IMT Double Tracking | CP032 | 2019-03-14 | 2000-01-01 | 2021-06-30 | 2021-06-30 | 0 | 0 | 635000 | 283000 | 0 | 352000 | 1 | 0
| San Francisco Municipal Transportation Agency | San Francisco Municipal Transportation Agency | Transit Capacity Expansion Program | CONST | Procurement of 8 Additional Expansion Light Rail Vehicles | CP006 | 2018-08-15 | 2015-01-01 | 2021-08-16 | 2000-01-01 | 0 | 0 | 26867000 | 11912000 | 0 | 14955000 | 1 | 0
| San Joaquin Joint Powers Authority and San Joaquin Regional Rail Commission | San Joaquin Regional Rail Commission | Valley Rail | CONST | Coach Car Procurement (4 + 8 Matching) | CP035 | 2019-10-09 | 2020-05-04 | 2023-05-04 | 2000-01-01 | 0 | 0 | 15500000 | 6886000 | 36166350.46 | 8614000 | 1 | 2.3333
[5 empty] | Design for BNSF Track Improvements | CP035 | 2021-03-25 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 0 | 0 | 18250000 | 8108000 | 36166350.46 | 10142000 | 0 | 1.9817
[5 empty] | Network Integration | CP035 | 2018-10-18 | 2000-01-01 | 2021-12-01 | 2000-01-01 | 0 | 0 | 1000000 | 0 | 36166350.46 | 1000000 | 1 | 36.1664
[5 empty] | Procurement, Station Construction, Track Expansion, Layover Facilities and Improvements (Multi-Year Funding) | CP035 | 2000-01-01 | 2022-09-30 | 2025-09-30 | 2000-01-01 | 0 | 0 | 0 | 0 | 36166350.46 | 0 | 1 | inf
|  |  |  | PA&ED | Design for BNSF Track Improvements | CP035 | 2021-03-25 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 0 | 0 | 1750000 | 777000 | 36166350.46 | 973000 | 0 | 20.6665
[5 empty] | Environmental Clearance and Preliminary Engineering for Multiple Stations | CP035 | 2018-10-18 | 2000-01-01 | 2021-06-30 | 2000-01-01 | 0.13151 | 500500000 | 12699000 | 5643000 | 36166350.46 | 7056000 | 1 | 2.848
[7 empty] | 2021-01-28 | 2000-01-01 | 2021-06-30 | 2000-01-01 | 0 | 0 | -7699000 | -3337000 | 36166350.46 | -4362000 | 0 | -4.6975
|  |  |  | PS&E | Design for BNSF Track Improvements | CP035 | 2020-05-14 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 0 | 0 | -450000 | -199000 | 36166350.46 | -251000 | 1 | -80.3697
[9 empty] | 2021-06-30 | 2000-01-01 | 0 | 0 | 450000 | 199000 | 36166350.46 | 251000 | 1 | 80.3697
[5 empty] | Final Design | CP035 | 2000-01-01 | 2000-01-01 | 2021-06-30 | 2000-01-01 | 0 | 0 | 0 | 0 | 36166350.46 | 0 | 1 | inf
[7 empty] | 2021-01-28 | 2000-01-01 | 2021-06-30 | 2000-01-01 | 0 | 0 | 7913000 | 3515000 | 36166350.46 | 4398000 | 0 | 4.5705
[7 empty] | 2021-03-25 | 2000-01-01 | 2021-06-30 | 2000-01-01 | 0 | 0 | 1952000 | 867000 | 36166350.46 | 1085000 | 0 | 18.5278
[5 empty] | Final Design (Oakley Station) | CP035 | 2018-10-18 | 2000-01-01 | 2021-06-30 | 2000-01-01 | 0 | 0 | 626000 | 278000 | 36166350.46 | 348000 | 1 | 57.7737
|  |  |  | R/W | Acquisition of Right of Way | CP035 | 2000-01-01 | 2000-01-01 | 2024-06-30 | 2000-01-01 | 0 | 0 | 0 | 0 | 36166350.46 | 0 | 1 | inf
[7 empty] | 2021-01-28 | 2000-01-01 | 2023-07-01 | 2000-01-01 | 0 | 0 | 9599000 | 4264000 | 36166350.46 | 5335000 | 0 | 3.7677
[7 empty] | 2021-03-25 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 0 | 0 | 4230000 | 1879000 | 36166350.46 | 2351000 | 0 | 8.55
| San Mateo County Transit District | San Mateo County Transit District | SamTrans Express Bus Pilot | CONST | Procurement of New Zero-Emission Electric Buses | CP078 | 2000-01-01 | 2022-12-31 | 2026-01-01 | 2000-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| Santa Barbara County Association of Governments | Santa Barbara County Association of Governments | Coastal Express/Pacific Surfliner Peak Hour Service Expansion and Integration Project | CONST | Procurement of Zero-Emission Buses | CP048 | 2020-06-25 | 2021-06-24 | 2024-06-24 | 2024-06-30 | 0 | 0 | 4300000 | 1906000 | 0 | 2394000 | 1 | 0
[5 empty] | Transit Facility Improvements for New Fleet and Services | CP048 | 2020-06-25 | 2020-12-31 | 2024-06-30 | 2024-06-30 | 0 | 0 | 1200000 | 532000 | 0 | 668000 | 1 | 0
|  |  |  | PS&E | Transit Facility Improvements for New Fleet and Services | CP048 | 2018-10-18 | 2000-01-01 | 2021-06-30 | 2021-06-30 | 1 | 9600000 | 300000 | 133000 | 0 | 167000 | 1 | 0
|  |  |  | R/W | Central Coast Regional Transit Facility | CP048 | 2020-06-25 | 2000-01-01 | 2022-06-25 | 2022-06-25 | 0 | 0 | 3800000 | 1684000 | 0 | 2116000 | 1 | 0
|  |  | Goleta Train Depot | CONST | Electric Shuttles and Associated Charging Station Infrastructure | CP047 | 2019-10-09 | 2021-03-30 | 2024-03-30 | 2021-03-30 | 0 | 0 | 400000 | 180000 | 638822.63 | 220000 | 1 | 1.5971
[5 empty] | Network Integration | CP047 | 2018-10-18 | 2018-10-18 | 2021-12-30 | 2021-12-30 | 0 | 0 | 250000 | 0 | 638822.63 | 250000 | 1 | 2.5553
|  |  |  | PA&ED | PA&ED for anw Multi-Modal Facility Adjacent to Existing Amtrak Train Station | CP047 | 2018-10-18 | 2000-01-01 | 2021-06-30 | 2021-06-30 | 0.16911 | 13009000 | 590000 | 266000 | 638822.63 | 324000 | 1 | 1.0828
[7 empty] | 2019-08-15 | 2000-01-01 | 2022-06-30 | 2022-06-30 | 0 | 0 | 960000 | 434000 | 638822.63 | 526000 | 1 | 0.66544
| Santa Clara Valley Transportation Authority | Santa Clara Valley Transportation Authority | VTA’s BART Silicon Valley Extension, Phase II | CONST | BART Rail Service Extension to San Jose (Multi-Year Funding) | CP057 | 2000-01-01 | 2000-01-01 | 2030-06-30 | 2000-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 1
[8 empty] | 2022-12-31 | 2030-06-30 | 2000-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| Shasta Regional Transportation Agency | Shasta Regional Transportation Agency | North State Intercity Bus System | CONST | Procurement of 7 Electric Coaches & Related Infrastructure | CP045 | 2018-10-18 | 2000-01-01 | 2026-01-01 | 2000-01-01 | inf | 0 | 8641000 | 3831000 | 0 | 4810000 | 1 | 0
| Solano Transportation Authority | Solano Transportation Authority | Solano Regional Transit Improvements | CONST | Capital Improvements for Improved Transit Service | CP046 | 2018-10-18 | 2018-11-15 | 2022-06-30 | 2000-01-01 | 0 | 0 | 5875000 | 2666000 | 3090500 | 3209000 | 1 | 0.52604
[5 empty] | Network Integration | CP046 | 2019-01-31 | 2019-10-08 | 2020-08-30 | 2000-01-01 | 0 | 0 | 250000 | 0 | 3090500 | 250000 | 1 | 12.362
[5 empty] | Vehicle Procurement - Pilot | CP046 | 2021-05-13 | 2021-05-18 | 2000-01-01 | 2024-05-13 | 0 | 0 | 1100000 | 499000 | 3090500 | 601000 | 0 | 2.8095
|  |  |  | PS&E | Charging Vehicle Infrastructure | CP046 | 2020-03-26 | 2000-01-01 | 2022-06-30 | 2000-01-01 | inf | 0 | 2000000 | 907000 | 3090500 | 1093000 | 1 | 1.5453
| Sonoma-Marin Area Rail Transit District | Sonoma-Marin Area Rail Transit District | SMART Larkspur to Windsor Corridor | CONST | Network Integration | CP041 | 2018-08-16 | 2018-09-19 | 2021-12-31 | 2022-12-01 | 0 | 0 | 1000000 | 0 | 11918142.74 | 1000000 | 1 | 11.9181
[5 empty] | Rail Extension to Windsor and Larkspur | CP041 | 2018-08-16 | 2018-09-19 | 2021-12-31 | 2022-12-01 | 1 | 21000000 | 20000000 | 9311000 | 11918142.74 | 10689000 | 1 | 0.59591
| Southern California Regional Rail Authority | Los Angeles County Metropolitan Transportation Authority | Southern California Optimized Rail Expansion (SCORE) | CONST | LINK US (Multi-Year Funding) | CP033 | 2000-01-01 | 2023-12-31 | 2027-12-31 | 2000-01-01 | 0 | 0 | 0 | 0 | 23748152.73 | 0 | 1 | inf
|  |  |  | PA&ED | LINK US | CP033 | 2018-10-18 | 2000-01-01 | 2021-12-31 | 2000-01-01 | 0.4159 | 875708000 | 23021000 | 10325000 | 23748152.73 | 12696000 | 1 | 1.0316
|  |  |  | PS&E | LINK US | CP033 | 2020-12-03 | 2000-01-01 | 2021-12-30 | 2000-01-01 | 0 | 0 | 67336000 | 29856000 | 23748152.73 | 37480000 | 0 | 0.35268
|  |  |  | R/W | LINK US | CP033 | 2019-08-15 | 2000-01-01 | 2022-06-30 | 2000-01-01 | 0 | 0 | 68531000 | 30737000 | 23748152.73 | 37794000 | 1 | 0.34653
[7 empty] | 2020-06-25 | 2000-01-01 | 2023-06-30 | 2000-01-01 | 0 | 0 | 68532000 | 30387000 | 23748152.73 | 38145000 | 1 | 0.34653
|  | Orange County Transportation Authority | Southern California Optimized Rail Expansion (SCORE) | PA&ED | Irvine Station Improvements | CP033 | 2021-06-24 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 0 | 0 | 6330000 | 2839000 | 23748152.73 | 3491000 | 0 | 3.7517
[5 empty] | Orange County Maintenance Facility, Ph 1a | CP033 | 2019-10-09 | 2000-01-01 | 2022-06-30 | 2000-01-01 | 0 | 0 | 4829000 | 2165000 | 23748152.73 | 2664000 | 1 | 4.9178
|  | Southern California Regional Rail Authority | Southern California Optimized Rail Expansion (SCORE) | CONST | Burbank Junction Speed Improvements | CP033 | 2021-03-25 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 0 | 0 | 16480000 | 7307000 | 23748152.73 | 9173000 | 0 | 1.441
[5 empty] | Chatsworth Station Improvements | CP033 | 2021-03-25 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 0 | 0 | 1500000 | 665000 | 23748152.73 | 835000 | 0 | 15.8321
[5 empty] | Construction Component for Wave 1B (Control Point Attwood to Katella) | CP033 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 0 | 0 | 0 | 0 | 23748152.73 | 0 | 1 | inf
[7 empty] | 2019-12-05 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 0 | 0 | 500000 | 224000 | 23748152.73 | 276000 | 1 | 47.4963
[7 empty] | 2021-01-28 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 0 | 0 | 329000 | 145000 | 23748152.73 | 184000 | 0 | 72.1828
[5 empty] | Fleet and Facility Improvements, Ph 1 (Multi-Year Funding) | CP033 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 0 | 0 | 0 | 0 | 23748152.73 | 0 | 1 | inf
[7 empty] | 2018-12-06 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 0 | 0 | 23160000 | 10387000 | 23748152.73 | 12773000 | 1 | 1.0254
[5 empty] | Fleet and Facility Improvements, Ph 2 | CP033 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 0 | 0 | 0 | 0 | 23748152.73 | 0 | 1 | inf
[5 empty] | LA to Fullerton Trunk Line, Track Improvements, for Wave 1A, Design/Build (Multi-Year Funding) | CP033 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 0 | 0 | 0 | 0 | 23748152.73 | 0 | 1 | inf
[7 empty] | 2018-12-06 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 0 | 0 | 5200000 | 2332000 | 23748152.73 | 2868000 | 1 | 4.567
[5 empty] | Network Integration | CP033 | 2018-10-18 | 2020-09-30 | 2023-06-30 | 2000-01-01 | 0 | 0 | 10000000 | 0 | 23748152.73 | 10000000 | 1 | 2.3748
[5 empty] | Rail Yard Rehabilitation & Modernization (Throat Segment) | CP033 | 2020-03-26 | 2021-06-30 | 2027-12-31 | 2000-01-01 | 0 | 0 | 19766000 | 8865000 | 23748152.73 | 10901000 | 1 | 1.2015
[5 empty] | Signal Respacing Burbank to LA | CP033 | 2021-03-25 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 0 | 0 | 6557000 | 2907000 | 23748152.73 | 3650000 | 0 | 3.6218
[5 empty] | WAVE 2: Siding, Station Improvements, Signals and Capacity Improvements | CP033 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 0 | 0 | 0 | 0 | 23748152.73 | 0 | 1 | inf
|  |  |  | PA&ED | El Monte Station Improvements | CP033 | 2021-01-28 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 0 | 0 | 140000 | 62000 | 23748152.73 | 78000 | 0 | 169.6297
[5 empty] | Environmental Assessment for Wave 1 and Wave 2 | CP033 | 2018-08-16 | 2000-01-01 | 2023-06-01 | 2000-01-01 | 0 | 0 | 6500000 | 2915000 | 23748152.73 | 3585000 | 1 | 3.6536
[5 empty] | Serra Siding Extension | CP033 | 2021-01-28 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 0 | 0 | 118000 | 52000 | 23748152.73 | 66000 | 0 | 201.2555
|  |  |  | PS&E | Burbank Junction Speed Improvements | CP033 | 2021-01-28 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 0 | 0 | 1092000 | 484000 | 23748152.73 | 608000 | 0 | 21.7474
[5 empty] | Design for Service Improvements Wave 1 and Wave 2 on the SB, VC, OC and LA Trunk lines (Multi-Year Funding) | CP033 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 0 | 0 | 0 | 0 | 23748152.73 | 0 | 1 | inf
[7 empty] | 2018-12-06 | 2000-01-01 | 2024-10-30 | 2000-01-01 | 0 | 0 | 29825000 | 13377000 | 23748152.73 | 16448000 | 1 | 0.79625
[5 empty] | Marengo Siding Improvements | CP033 | 2021-03-25 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 0 | 0 | 522000 | 231000 | 23748152.73 | 291000 | 0 | 45.4945
|  |  |  | R/W | Chatsworth Station Improvements | CP033 | 2021-01-28 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 0 | 0 | 3585000 | 1589000 | 23748152.73 | 1996000 | 0 | 6.6243
[5 empty] | Construction Component for Wave 1B (Control Point Attwood to Katella) | CP033 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 0 | 0 | 0 | 0 | 23748152.73 | 0 | 1 | inf
[5 empty] | Marengo Siding Improvements | CP033 | 2021-03-25 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 0 | 0 | 354000 | 156000 | 23748152.73 | 198000 | 0 | 67.0852
| Transportation Agency for Monterey County | Transportation Agency for Monterey County | Rail Extension to Monterey County | CONST | Network Integration | 1155 | 2018-10-18 | 2019-04-24 | 2022-04-24 | 2000-01-01 | 0 | 0 | 500000 | 0 | 0 | 500000 | 1 | 0
[5 empty] | New Passenger Rail Service to Salinas | 1155 | 2000-01-01 | 2023-12-01 | 2026-12-01 | 2000-01-01 | 0.049271 | 10148000 | 0 | 0 | 0 | 0 | 1
[5 empty] | Positive Train Control | 1155 | 2000-01-01 | 2023-12-01 | 2026-12-01 | 2000-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 1
2020 | Antelope Valley Transit Authority | Antelope Valley Transit Authority | Reaching the Most Transit-Vulnerable: AVTA's Zero Emission "Microtransit" & Bus Expansion Proposal | CONST | Network Integration | CP059 | 2020-08-12 | 2000-01-01 | 2023-08-12 | 2023-08-12 | 0 | 0 | 250000 | 0 | 0 | 250000 | 0 | 0
[5 empty] | Purchase of 11 Zero-Emission Vehicles and Supporting Infrastructure | CP059 | 2020-08-12 | 2000-01-01 | 2023-08-12 | 2023-08-12 | 1 | 6503000 | 6253000 | 3251000 | 0 | 3002000 | 0 | 0
| Bay Area Rapid Transit District | Bay Area Rapid Transit District | The Transbaby Corridor Core Capacity Program: Vehicle Acquisition | CONST | Acquisition of 34 rail vehicles to support service capacity | CP060 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 0 | 107100000 | 0 | 0 | 0 | 0 | 1
| Capitol Corridor Joint Powers Authority | Capitol Corridor Joint Powers Authority | Sacramento Valley Station (SVS) Transit Center | CONST | Network Integration | CP061 | 2020-08-12 | 2020-12-01 | 2022-02-28 | 2023-08-12 | 0 | 0 | 720000 | 0 | 0 | 720000 | 0 | 0
[5 empty] | New Northside station access | CP061 | 2021-12-31 | 2022-06-30 | 2025-06-30 | 2000-01-01 | 0.18396 | 3914000 | 0 | 0 | 0 | 0 | 0
| City of Inglewood | City of Inglewood | Inglewood Transit Connector Project | CONST | Automated People Mover | CP062 | 2022-12-31 | 2023-12-31 | 2026-11-01 | 2000-01-01 | 0 | 0 | 0 | 0 | 1823462.51 | 0 | 0 | inf
|  |  |  | PA&ED | Automated People Mover | CP062 | 2020-08-13 | 2000-01-01 | 2023-06-30 | 2023-06-30 | 0.21008 | 95200000 | 20000000 | 10000000 | 1823462.51 | 10000000 | 0 | 0.091173
| City of Santa Monica | City of Santa Monica | For People, Place and Planet: Connecting Inglewood to Regional Opportunities | CONST | Procurement of 7 zero-emission buses | CP071 | 2000-01-01 | 2022-06-30 | 2024-12-01 | 2000-01-01 | 0 | 1105000 | 0 | 0 | 0 | 0 | 1
| Lake Transit Authority | Lake Transit Authority | North State Intercity Bus System | PA&ED | New transit center, 4 new EV buses, expanded service routes, new infrastructure at maintenance facility | CP063 | 2020-12-31 | 2000-01-01 | 2026-01-31 | 2023-06-30 | 0.01924 | 12994000 | 250000 | 125000 | 0 | 125000 | 0 | 0
| Long Beach Transit | Long Beach Transit | LBT/UCLA Electric Commuter Express | CONST | Purchase 5 zero-emission battery electric coaches | CP064 | 2021-05-13 | 2022-12-31 | 2025-12-01 | 2024-05-13 | 1 | 6451000 | 6451000 | 3225000 | 0 | 3226000 | 0 | 0
| Los Angeles County Metropolitan Transportation Authority and Southern California Regional Rail Authority | Los Angeles County Metropolitan Transportation Authority | Metrolink Antelope Valley Line Capital and Service Improvements | CONST | Balboa Double Track Extension/Lancaster Terminal Improvements | CP065 | 2025-12-31 | 2026-12-31 | 2027-06-01 | 2000-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Canyon Siding Extension/Brighton-McGinley Double Track | CP065 | 2025-12-31 | 2026-12-31 | 2027-06-01 | 2000-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Zero-Emission Multiple Units (Pilot) | CP065 | 2022-12-31 | 2023-12-31 | 2025-06-01 | 2000-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | R/W | Balboa Double Track Extension/Lancaster Terminal Improvements | CP065 | 2023-12-31 | 2000-01-01 | 2027-12-31 | 2000-01-01 | 0 | 107050000 | 0 | 0 | 0 | 0 | 0
[5 empty] | Canyon Siding Extension/Brighton-McGinley Double Track | CP065 | 2022-12-31 | 2000-01-01 | 2026-12-31 | 2000-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Los Angeles-San Diego-San Luis Obispo Rail Corridor Agency (LOSSAN) | Los Angeles-San Diego-San Luis Obispo Rail Corridor Agency (LOSSAN) | Building Up Control: LOSSAN Service Enhancement Program | CONST | Central Coast Layover Facility Expansion | CP066 | 2023-12-31 | 2024-12-31 | 2026-12-01 | 2000-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | San Diego County Maintenance and Layover Facility | CP066 | 2022-12-31 | 2023-12-31 | 2026-01-01 | 2000-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | PA&ED | San Diego County Maintenance and Layover Facility | CP066 | 2020-12-31 | 2000-01-01 | 2025-06-30 | 2000-01-01 | 0 | 38743000 | 0 | 0 | 0 | 0 | 0
|  |  |  | PS&E | Central Coast Layover Facility Expansion | CP066 | 2021-12-31 | 2000-01-01 | 2025-12-31 | 2000-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | San Diego County Maintenance and Layover Facility | CP066 | 2021-12-31 | 2000-01-01 | 2025-12-31 | 2000-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sacramento Regional Transit District | Sacramento Regional Transit District | Light Rail Modernization and Expansion of Low-Floor Fleet | CONST | Acquisition of light rail vehicles | CP067 | 2021-08-19 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 1 | 23600000 | 23600000 | 11800000 | 0 | 11800000 | 0 | 0
| San Bernardino County Transportation Authority (SBCTA) and Omnitrans | San Bernardino County Transportation Authority (SBCTA) and Omnitrans | West Valley Connector Bus Rapid Transit Phase 1 & ZEB Initiative | CONST | Acquisition of zero-emission buses | CP068 | 2021-12-31 | 2022-12-31 | 2023-12-01 | 2000-01-01 | 0 | 15000000 | 0 | 0 | 0 | 0 | 0
| San Diego Association of Governments (SANDAG) | San Diego Association of Governments (SANDAG) | SDConnect: San Diego Rail Improvement Program | CONST | Del Mar Bluffs Stabilization | CP069 | 2021-12-31 | 2022-12-31 | 2025-01-01 | 2000-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | PS&E | Del Mar Bluffs Stabilization | CP069 | 2020-08-13 | 2000-01-01 | 2023-06-30 | 2023-06-30 | 0.3714 | 12100000 | 3774000 | 1887000 | 0 | 1887000 | 0 | 0
|  | San Diego Metropolitan Transit System (MTS) | SDConnect: San Diego Rail Improvement Program | CONST | El Cajon Third Track | CP069 | 2021-12-31 | 2022-12-31 | 2023-06-01 | 2000-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | PS&E | El Cajon Third Track | CP069 | 2020-10-22 | 2000-01-01 | 2023-06-30 | 2023-06-30 | 0 | 0 | 720000 | 360000 | 0 | 360000 | 0 | 0
| San Francisco Bay Area Water Emergency Transportation Authority | San Francisco Bay Area Water Emergency Transportation Authority | Expansion of WETA Ferry Services | CONST | Acquisition of a new all-electric vessels and supporting infrastructure | CP075 | 2020-12-31 | 2021-06-01 | 2025-06-01 | 2000-01-01 | 0 | 9060000 | 0 | 0 | 0 | 0 | 0
| San Francisco Municipal Transportation Agency | San Francisco Municipal Transportation Agency | Core Capacity Program | CONST | MUNI Forward J Line | CP070 | 2024-12-31 | 2025-12-31 | 2027-12-01 | 2000-01-01 | 0 | 41668000 | 0 | 0 | 0 | 0 | 0
[5 empty] | MUNI Forward M Line | CP070 | 2024-12-31 | 2025-12-31 | 2027-12-01 | 2000-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Solano Transportation Authority | Solano Transportation Authority | Solano Regional Transit Improvements Phase 2 | CONST | Access Improvements at Fairfield Transit Center | CP072 | 2021-12-31 | 2022-12-31 | 2025-03-01 | 2000-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Access Improvements at Fairfield-Vacaville Stations | CP072 | 2021-12-31 | 2022-12-31 | 2025-01-01 | 2000-01-01 | 0 | 0 | 400000 | 200000 | 0 | 200000 | 0 | 0
[5 empty] | Access Improvements at Vacaville Transit Center | CP072 | 2021-12-31 | 2022-12-31 | 2025-01-01 | 2000-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Network Integration | CP072 | 2020-10-22 | 2022-06-30 | 2024-03-01 | 2000-01-01 | 0 | 0 | 1100000 | 0 | 0 | 1100000 | 0 | 0
[5 empty] | Shared Inductive Charging Infrastructure | CP072 | 2021-12-31 | 2022-12-31 | 2025-01-01 | 2000-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | PS&E | Access Improvements at Fairfield Transit Center | CP072 | 2021-05-13 | 2000-01-01 | 2025-06-30 | 2023-06-30 | 0.27885 | 10400000 | 400000 | 200000 | 0 | 200000 | 0 | 0
[5 empty] | Shared Inductive Charging Infrastructure | CP072 | 2020-10-22 | 2000-01-01 | 2025-06-30 | 2000-01-01 | 0 | 0 | 1000000 | 500000 | 0 | 500000 | 0 | 0
| Torrance Transit Department | Torrance Transit Department | Torrance Transit Bus Service Enhancement Program | CONST | Procurement of 7 zero-emission buses | CP073 | 2020-10-22 | 2021-03-01 | 2021-12-31 | 2000-01-01 | 1 | 6000000 | 6000000 | 3000000 | 0 | 3000000 | 0 | 0
| Transit Joint Powers Authority for Merced County | Transit Joint Powers Authority for Merced County | Improving Air Quality & Economic Growth with Electric Buses in Merced County, the Gateway to Yosemite | CONST | Procurement of 3 zero-emission buses | CP074 | 2020-10-22 | 2000-01-01 | 2026-01-31 | 2023-10-22 | 1 | 3112000 | 3112000 | 1556000 | 0 | 1556000 | 0 | 0