## Summary
| 2015 | 2016 | 2018 | 2020 | Grand_Total
Number_of_Awarded_Projects | 14 | 15 | 28 | 17 | 74
Award_Amount | 224328000 | 788444000 | 4251722000 | 500000000 | 5764494000
Allocated_Amount | 224278000 | 422477816 | 1627802000 | 74030000 | 2348587816
Expended_Amount | 143556084.9 | 119517737.55 | 210456649.72 | 1823462.51 | 475353934.68
Expended_Percent_of_Awarded | 63.9938 | 15.1587 | 4.9499 | 0.36469 | 8.2462
Expended_Percent_of_Allocated | 64.0081 | 28.2897 | 12.9289 | 2.4631 | 20.24
Percent_Allocated | 99.9777 | 53.5837 | 38.2857 | 14.806 | 40.7423

## FY
Award_Year | Project_# | Award_Recipient | Implementing_Agency | Project_Title | TIRCP_Award_Amount | Percent_of_Award_Fully_Allocated | Components | PPNO | Phase | Allocation_Date | CON_Contract_Award_Date | Completion_Date | Phase_Completion_Date | Allocation_Allocation_Sheet | GGRF_Funding | Expended_ALLOCATION | PTA-SB1 Allocation Amount | Percent_of_Allocation_Expended | Allocated_Before_July_2020_1_is_yes
2015 | 1 | Antelope Valley Transit Authority | Antelope Valley Transit Authority | Regional Transit Interconnectivity & Environmental Sustability | 24403000 | 100 | Purchase 13 60-foot articulated BRT buses and 16 45-foot electric commuter buses | CP005 | CONST | 2015-10-22 | 2016-03-14 | 2022-03-30 | 2022-03-31 | 24403000 | 24403000 | 21714177.53 | 0 | 88.9816 | 1
| 2 | Capitol Corridor Joint Powers Authority | Capitol Corridor Joint Powers Authority | Travel Time Reduction Project | 4620000 | 100 | Track and curve improvements between San Jose and Martinez for faster journeys benefiting Capitol Corridor passengers | CP012 | CONST | 2016-05-19 | 2016-06-01 | 2019-06-01 | 2019-06-01 | 4620000 | 4620000 | 4619999.9 | 0 | 100 | 1
| 3 | Los Angeles County Metropolitan Transportation Authority | Los Angeles County Metropolitan Transportation Authority | Willowbrook/Rosa Parks Station & Blue Line Light Rail Operational Improvements Project | 38494000 | 100 | Replace Blue Line signal system; install new track crossovers, new train controls at 15 locations, new LED signals and power switches, 19 turnouts, new track, overhead catenary, and a communications upgrade. | CP015 | CONST | 2016-06-30 | 2017-06-28 | 2021-06-30 | 2020-06-28 | 38494000 | 38494000 | 38494000 | 0 | 100 | 1
| 4 | Los Angeles-San Diego-San Luis Obispo Rail Corridor Agency (LOSSAN) | Los Angeles-San Diego-San Luis Obispo Rail Corridor Agency (LOSSAN) | Pacific Surfliner Transit Transfer Program | 1675000 | 100 | LOSSAN and 12 transit agencies from San Luis Obispo to San Diego counties to use seamless ticketing to increase use of transit | CP007 | CONST | 2015-12-10 | 2016-06-01 | 2021-06-30 | 2021-06-30 | 1675000 | 1675000 | 277840.47 | 0 | 16.5875 | 1
| 5 | Monterey-Salinas Transit | Monterey-Salinas Transit | Monterey Bay Operations and Maintenance Facility/Salinas Transit Service Project | 10000000 | 100 | Renovation and expansion of the Monterey maintenance and operations facility. | CP013 | CONST | 2016-05-19 | 2016-11-03 | 2018-09-30 | 2019-11-03 | 10000000 | 10000000 | 0 | 0 | 0 | 1
| 6 | Orange County Transportation Authority (OCTA) | Orange County Transportation Authority (OCTA) | Bravo! Route 560 Rapid Buses | 2320000 | 100 | Purchase five 40-foot CNG buses for BRT Route linking SARTC to Metrolink/Amtrak | CP004 | CONST | 2015-10-22 | 2015-11-30 | 2018-02-11 | 2018-11-30 | 2320000 | 2320000 | 0 | 0 | 0 | 1
| 7 | Sacramento Regional Transit District | Sacramento Regional Transit District | Sacramento Regional Transit's Refurbishment of 7 Light Rail Vehicles | 6427000 | 100 | Refurbishment of Seven UTDC Light Rail Vehicles Used Throughout the System | CP001 | CONST | 2015-08-27 | 2015-10-21 | 2020-06-30 | 2020-06-30 | 6427000 | 6427000 | 0 | 0 | 0 | 1
| 8 | San Diego Association of Governments (SANDAG) | San Diego Association of Governments (SANDAG) | South Bay Bus Rapid Transit | 4000000 | 100 | Bus Rapid Transit Route between Downtown San Diego and the Otay Mesa Crossing | CP003 | CONST | 2015-08-27 | 2016-01-08 | 2020-09-30 | 2019-01-08 | 4000000 | 4000000 | 4000000 | 0 | 100 | 1
| 9 | San Diego Metropolitan Transit System (MTS) | San Diego Metropolitan Transit System (MTS) | San Diego Metropolitan Transit System Trolley Capacity Improvements | 31986000 | 99.8437 | Courthouse Trolley Station (Construction) | CP008 | CONST | 2017-06-29 | 2017-05-30 | 2020-06-29 | 2020-06-29 | 3760000 | 3760000 | 0 | 0 | 0 | 1
[7 empty] | Courthouse Trolley Station (Design) | CP008 | PS&E | 2016-01-21 | 2100-01-01 | 2018-06-30 | 2018-06-30 | 713000 | 713000 | 713000 | 0 | 100 | 1
[7 empty] | Purchase 8 trolley vehicles to expand service on the Blue and Orange lines | CP008 | CONST | 2016-10-20 | 2016-11-01 | 2019-11-01 | 2019-11-01 | 27463000 | 27463000 | 27463000 | 0 | 100 | 1
| 10 | San Francisco Municipal Transportation Agency | San Francisco Municipal Transportation Agency | SFMTA Light Rail Vehicle Fleet Expansion | 41181000 | 100 | Purchase 8 Zero-emission Light Rail Vehicles for MUNI Service Expansion | CP006 | CONST | 2015-12-10 | 2015-01-01 | 2018-12-10 | 2018-12-10 | 41181000 | 41181000 | 0 | 0 | 0 | 1
| 11 | San Joaquin Regional Rail Commission | San Joaquin Regional Rail Commission | ACE Wayside Power Project | 200000 | 100 | Installation of wayside power sources at ACE’s new Regional Maintenance Facility in Stockton | CP014 | CONST | 2018-01-31 | 2018-02-02 | 2019-11-13 | 2021-02-02 | 185000 | 185000 | 185000 | 0 | 100 | 1
[9 empty] | PS&E | 2017-08-17 | 2100-01-01 | 2019-11-13 | 2020-06-30 | 15000 | 15000 | 15000 | 0 | 100 | 1
| 12 | San Joaquin Regional Transit District | San Joaquin Regional Transit District | Bus Rapid Transit – Martin Luther King Corridor and Crosstown Miner Corridor | 6841000 | 100 | Bus rapid transit infrastructure along the MLK Corridor and Crosstown Miner Corridor, including the acquisition of 12 new zero-emission electric vehicles | CP011 | CONST | 2017-01-19 | 2017-06-23 | 2020-03-30 | 2020-06-23 | 6841000 | 6841000 | 6841000 | 0 | 100 | 1
| 13 | Southern California Regional Rail Authority (Metrolink) | Southern California Regional Rail Authority (Metrolink) | Purchase of Nine Fuel-Efficient Tier IV EMD F-125 Locomotives | 41181000 | 100 | Purchase nine of 20 locomotives that complete Metrolink's replacement program and expand service with three locomotives. | CP002 | CONST | 2016-03-17 | 2015-10-15 | 2022-09-30 | 2021-09-30 | 41181000 | 41181000 | 37583067 | 0 | 91.2631 | 1
| 14 | Sonoma-Marin Area Rail Transit District | Sonoma-Marin Area Rail Transit District | SMART Rail Car Capacity Project | 11000000 | 100 | Purchase four rail cars, two "A"cars and two "B" cars, for expansion of SMART's fleet | CP010 | CONST | 2016-03-17 | 2016-04-06 | 2021-12-30 | 2100-01-01 | 11000000 | 11000000 | 1650000 | 0 | 15 | 1
2016 | 1 | Antelope Valley Transit Authority | SunLine Transit Agency | Zero Emission Bus and Vanpool Expansion in the Antelope Valley, Kern County and the Coachella Valley | 6481000 | 137.7874 | Purchase 4 zero-emission buses to be operated by SunLine Transit within Coachella Valley | CP019 | CONST | 2017-01-19 | 2017-05-16 | 2100-01-01 | 2020-05-16 | 2449000 | 2449000 | 2449000 | 0 | 100 | 1
| 2 | Capitol Corridor Joint Powers Authority | Capitol Corridor Joint Powers Authority | Increased Rail Service to Roseville, Service Optimization and Standby Power Investments | 8999000 | 38.2931 | Install 2 Standby Power Cabinets | CP023 | CONST | 2017-03-16 | 2019-01-09 | 2024-06-30 | 2021-01-09 | 200000 | 200000 | 0 | 0 | 0 | 1
[7 empty] | Optimization Study | CP023 | CONST | 2017-05-17 | 2017-06-01 | 2021-06-30 | 2020-05-23 | 320000 | 320000 | 172650.41 | 0 | 53.9533 | 1
[13 empty] | 2021-06-30 | 0 | 0 | 172650.41 | 0 |  | 1
[7 empty] | Sacramento to Roseville 3rd Mainline Track | CP023 | CONST | 2100-01-01 | 2100-01-01 | 2100-01-01 | 2100-01-01 | 0 | 0 | 0 | 0 |  | 1
[9 empty] | PS&E | 2017-06-29 | 2100-01-01 | 2100-01-01 | 2019-06-30 | 886000 | 886000 | 0 | 0 | 0 | 1
[13 empty] | 2021-02-28 | 0 | 0 | 0 | 0 |  | 1
[13 empty] | 2024-02-28 | 0 | 0 | 0 | 0 |  | 1
[10 empty] | 2018-08-16 | 2100-01-01 | 2100-01-01 | 2021-02-28 | 2000000 | 2000000 | 93803.62 | 0 | 4.6902 | 1
[13 empty] | 2024-02-28 | 0 | 0 | 93803.62 | 0 |  | 1
[9 empty] | R/W | 2017-06-29 | 2100-01-01 | 2100-01-01 | 2019-06-30 | 40000 | 40000 | 0 | 0 | 0 | 1
[13 empty] | 2021-02-28 | 0 | 0 | 0 | 0 |  | 1
[13 empty] | 2024-02-28 | 0 | 0 | 0 | 0 |  | 1
| 3 | Foothill Transit | Foothill Transit | Transforming California: Bus Electrification, Service Expansion and Rail Integration | 5000000 | 100 | Purchase 20 zero-emission electric buses to extend Route 486 to Pomona Metrolink Station and increase frequencies | CP076 | CONST | 2021-06-24 | 2100-01-01 | 2024-06-01 | 2024-06-24 | 5000000 | 5000000 | 0 | 0 | 0 | 0
| 4 | City of Fresno | City of Fresno | Metropolitan Rapid Transit and Rail Connectivity Project | 8000000 | 100 | Bus Stop Improvements | CP016 | CONST | 2020-06-25 | 2100-01-01 | 2024-06-24 | 2023-06-25 | 3917000 | 3917000 | 0 | 0 | 0 | 1
[7 empty] | Modernize Fare Payment Systems | CP016 | CONST | 2016-12-08 | 2017-01-13 | 2022-12-30 | 2022-12-30 | 4083000 | 4083000 | 0 | 0 | 0 | 1
| 5 | Los Angeles County Metropolitan Transportation Authority | Los Angeles County Metropolitan Transportation Authority | Airport Metro Connector 96th Street Station/Metro Green Line Extension to LAX | 40000000 | 100 | Construct New Station to Connect LAX People Mover to Metro Green Line, Crenshaw Line and Buses | CP058 | CONST | 2020-06-25 | 2100-01-01 | 2025-07-30 | 2024-07-31 | 40000000 | 40000000 | 0 | 0 | 0 | 1
| 6 | Los Angeles County Metropolitan Transportation Authority | Los Angeles County Metropolitan Transportation Authority | Metro Red Line and Purple Line Core Capacity Improvements | 69209000 | 100.3424 | Construction | CP020 | CONST | 2019-12-05 | 2020-03-26 | 2024-07-25 | 2024-07-31 | 64437000 | 64437000 | 0 | 0 | 0 | 1
[7 empty] | Environmental assessment | CP020 | PA&ED | 2017-01-19 | 2100-01-01 | 2022-06-30 | 2019-06-30 | 1908000 | 1908000 | 1119881.34 | 0 | 58.694 | 1
[7 empty] | Final design | CP020 | PS&E | 2017-06-29 | 2100-01-01 | 2019-05-21 | 2100-01-01 | 3101000 | 3101000 | 3101000 | 0 | 100 | 1
| 7 | Los Angeles-San Diego-San Luis Obispo Rail Corridor Agency (LOSSAN) | San Diego Association of Governments (SANDAG) | All Aboard: Transforming Southern California Rail Travel | 82000000 | 90.8049 | Elvira to Morena Double Track | CP021 | CONST | 2017-03-16 | 2017-02-28 | 2022-10-31 | 2020-03-16 | 49995000 | 49995000 | 49622714.33 | 0 | 99.2554 | 1
[10 empty] | 2018-02-01 | 2017-02-28 | 2022-10-31 | 2100-01-01 | 11988000 | 11988000 | 11760285.67 | 0 | 98.1005 | 1
| 8 | Orange County Transportation Authority (OCTA) | Orange County Transportation Authority (OCTA) | OC Streetcar and OCTA System-Wide Mobile Ticketing | 28000000 | 100 | Mobile ticketing implementation on fixed route bus system | CP017 | CONST | 2016-10-20 | 2016-11-21 | 2018-02-01 | 2019-11-21 | 2482000 | 2482000 | 0 | 0 | 0 | 1
[7 empty] | New line connecting SARTC with new multimodal hub at Harbor Blvd, 8 LRVs | CP017 | CONST | 2018-05-17 | 2018-11-19 | 2022-10-31 | 2021-02-28 | 25518000 | 25518000 | 0 | 0 | 0 | 1
| 9 | Peninsula Corridor Joint Powers Board | Peninsula Corridor Joint Powers Board | Peninsula Corridor Electrification Project | 20000000 | 100 | Electrify Caltrain Corridor and Procurement of electric multiple unit vehicles | CP022 | CONST | 2017-06-29 | 2016-08-15 | 2022-08-22 | 2022-08-22 | 20000000 | 20000000 | 14102518.86 | 0 | 70.5126 | 1
| 10 | Sacramento Regional Transit District | Sacramento Regional Transit District | Downtown/Riverfront Sacramento-West Sacramento Streetcar | 30000000 | 0 | Construct new streetcar line linking Sacramento and West Sacramento | CP080 | CONST | 2026-12-31 | 2100-01-01 | 2100-01-01 | 2100-01-01 | 0 | 0 | 0 | 0 |  | 0
| 11 | San Bernardino County Transportation Authority (SBCTA) | San Bernardino County Transportation Authority (SBCTA) | Redlands Passenger Rail Project | 9204000 | 100 | Construct new Rail System linking San Bernardino and the University of Redlands | 1230 | CONST | 2018-10-18 | 2019-05-15 | 2022-07-31 | 2022-06-01 | 9204000 | 9204000 | 9204000 | 0 | 100 | 1
| 12 | San Francisco Municipal Transportation Agency | San Francisco Municipal Transportation Agency | Light Rail Modernization and Expansion Program | 45092000 | 100 | Purchase 10 Expansion Light Rail Vehicles to Increase Capacity and Improve Service | CP006 | CONST | 2017-05-18 | 2015-01-01 | 2020-05-07 | 2100-01-01 | 45092000 | 45092000 | 0 | 0 | 0 | 1
| 13 | San Joaquin Regional Rail Commission | San Joaquin Regional Rail Commission | ACE Near-Term Capacity Improvement Program | 16459000 | 48.6056 | Platforms (Construction) | CP025 | CONST | 2100-01-01 | 2100-01-01 | 2100-01-01 | 2100-01-01 | 0 | 0 | 0 | 0 |  | 1
[7 empty] | Platforms (PA&ED-exempt) | CP025 | PA&ED | 2018-06-28 | 2100-01-01 | 2100-01-01 | 2020-06-30 | 0 | 0 | 0 | 0 |  | 1
[7 empty] | Platforms (PS&E) | CP025 | PS&E | 2018-06-28 | 2100-01-01 | 2022-01-01 | 2020-06-30 | 500000 | 500000 | 0 | 0 | 0 | 1
[7 empty] | Procurement of Tier IV Locomotives | CP025 | CONST | 2017-08-17 | 2018-04-20 | 2021-04-20 | 2021-04-20 | 7500000 | 7500000 | 0 | 0 | 0 | 1
| 14 | Santa Clara Valley Transportation Authority | Santa Clara Valley Transportation Authority | BART Silicon Valley Phase II Extension | 20000000 | 0 | Procurement of BART Vehicles for BART to San Jose Extension | CP057 | CONST | 2100-01-01 | 2023-12-30 | 2030-06-01 | 2100-01-01 | 0 | 0 | 0 | 0 |  | 1
| 15 | San Joaquin Regional Rail Commission | San Joaquin Regional Rail Commission | SB 132 ACE Extension Lathrop to Ceres/Merced | 400000000 | 25.725 | PA&ED Consulting Services | CP026 | PA&ED | 2100-01-01 | 2020-02-07 | 2027-12-01 | 2100-01-01 | 16752568 | 0 | 16750768 | 0 | 99.9893 | 1
[7 empty] | PS&E for Stations, track work, and layover facilities | CP026 | PS&E | 2100-01-01 | 2020-02-07 | 2027-12-01 | 2100-01-01 | 34006667 | 0 | 0 | 0 | 0 | 1
[7 empty] | Procurement of Two Tier IV locomotives | CP026 | CONST | 2100-01-01 | 2020-02-07 | 2027-12-01 | 2100-01-01 | 14698284 | 0 | 0 | 0 | 0 | 1
[7 empty] | Procurement of bi-level cab cars | CP026 | CONST | 2100-01-01 | 2020-02-07 | 2027-12-01 | 2100-01-01 | 19000000 | 0 | 0 | 0 | 0 | 1
[7 empty] | ROW for Stations and layover facilities | CP026 | ROW | 2100-01-01 | 2020-02-07 | 2027-12-01 | 2100-01-01 | 5152297 | 0 | 0 | 0 | 0 | 1
[7 empty] | Working Capital | CP026 | CONST | 2100-01-01 | 2020-02-07 | 2027-12-01 | 2100-01-01 | 13290000 | 0 | 0 | 0 | 0 | 1
2018 | 1 | Alameda Contra Costa Transit District | Alameda Contra Costa Transit District | Purchase Zero Emission High Capacity Buses to Support Transbay Tomorrow and Clean Corridors Plan | 14000000 | 57.1429 | Facilities and bus charging infrastructure | 2320B | CONST | 2100-01-01 | 2100-01-01 | 2100-01-01 | 2100-01-01 | 0 | 0 | 0 | 0 |  | 1
[9 empty] | PS&E | 2020-10-22 | 2020-11-01 | 2021-10-01 | 2100-01-01 | 1000000 | 459000 | 0 | 541000 | 0 | 0
[7 empty] | Network Integration | 2320B | CONST | 2018-10-18 | 2019-04-19 | 2020-06-30 | 2100-01-01 | 500000 | 0 | 500000 | 500000 | 100 | 1
[7 empty] | Zero-Emission Buses for Service Expansion | 2320B | CONST | 2020-10-22 | 2020-11-01 | 2024-04-01 | 2100-01-01 | 6500000 | 2988000 | 0 | 3512000 | 0 | 0
| 2 | Anaheim Transportation Network (ATN) | Anaheim Transportation Network (ATN) | #Electrify Anaheim: Changing the Transit Paradigm in Southern California | 28617000 | 100 | 10 Micro transit Electric Vehicles, Signage & Mobile App Development | CP027 | CONST | 2018-08-16 | 2019-02-13 | 2020-06-30 | 2020-06-30 | 802000 | 355000 | 610535.78 | 447000 | 76.1267 | 1
[7 empty] | 40 Zero-Emission Electric Buses | CP027 | CONST | 2018-12-06 | 2019-07-23 | 2023-06-30 | 2023-06-30 | 22857000 | 10134000 | 13492703.78 | 12723000 | 59.0309 | 1
[7 empty] | Construction of New O&M facility with Solar Canopy to Charge Zero-Emission Vehicles | CP027 | CONST | 2019-10-09 | 2020-04-03 | 2023-04-03 | 2021-06-01 | 4958000 | 2198000 | 1726120.92 | 2760000 | 34.8149 | 1
| 3 | Antelope Valley Transit Authority & Long Beach Transit | Antelope Valley Transit Authority | From the Desert to the Sea: Antelope Valley Transit Authority and Long Beach Transit Zero Emission Bus Initiative | 9205000 | 100 | 7 Zero-Emission Electric Buses and Upgrades to Supporting Infrastructure | CP028 | CONST | 2018-10-18 | 2019-07-02 | 2021-07-31 | 2021-07-31 | 7755000 | 3505000 | 2584518.66 | 4250000 | 33.3271 | 1
[7 empty] | Facility Improvements | CP028 | CONST | 2020-05-14 | 2020-07-13 | 2023-07-13 | 2023-07-13 | 1200000 | 542000 | 0 | 658000 | 0 | 1
[7 empty] | Network Integration | CP028 | CONST | 2018-10-18 | 2019-01-07 | 2022-01-07 | 2022-01-07 | 250000 | 0 | 57296.59 | 250000 | 22.9186 | 1
| 4 | Bay Area Rapid Transit District | Bay Area Rapid Transit District | The Transbay Corridor Core Capacity Program: Vehicle Acquistion and Communications-Based Train Control System | 318600000 | 115.6937 | New BART Rail Vehicles and Communication-Based Train Control System for Improved Service(Acquisition of 272 new rail vehicles and communication- based train control systems to allow for increase service frequency) | CP055 | CONST | 2019-12-05 | 2020-09-16 | 2030-01-01 | 2030-12-30 | 51492000 | 22831000 | 0 | 28661000 | 0 | 1
[10 empty] | 2021-05-14 | 2020-09-16 | 2030-01-01 | 2030-12-30 | 267108000 | 118436000 | 0 | 148672000 | 0 | 0
[10 empty] | 2100-01-01 | 2100-01-01 | 2100-01-01 | 2100-01-01 | 50000000 | 0 | 0 | 50000000 | 0 | 1
| 5 | Capitol Corridor Joint Powers Authority | Capitol Corridor Joint Powers Authority | The Northern California Corridor Enhancement Program | 80340000 | 62.2853 | Integrated Travel Program for Statewide Service and Ticket Integration | CP036 | CONST | 2018-08-16 | 2100-01-01 | 2021-12-25 | 2019-02-15 | 6000000 | 2660000 | 4838990.29 | 3340000 | 80.6498 | 1
[10 empty] | 2018-12-06 | 2019-01-18 | 2021-12-25 | 2023-12-31 | 0 | 0 | 4838990.29 | 0 |  | 1
[11 empty] | 2100-01-01 | 2021-12-25 | 2019-02-15 | 0 | 68000 | 4838990.29 | -68000 | inf | 1
[7 empty] | Integrated Travel Program for Statewide Service and Ticket Integration (Ph 3b & 4) | CP036 | CONST | 2020-05-14 | 2020-05-14 | 2021-12-25 | 2024-12-31 | 21340000 | 9702000 | 0 | 11638000 | 0 | 1
[7 empty] | Network Integration | CP036 | CONST | 2018-12-06 | 2019-03-27 | 2020-11-30 | 2020-11-30 | 2000000 | 0 | 476432.37 | 2000000 | 23.8216 | 1
[12 empty] | 2021-12-23 | 2023-12-31 | 0 | 0 | 476432.37 | 0 |  | 1
[7 empty] | South Bay Connector Project | CP036 | CONST | 2100-01-01 | 2100-01-01 | 2021-12-26 | 2100-01-01 | 0 | 0 | 0 | 0 |  | 1
[9 empty] | PA&ED | 2018-08-16 | 2100-01-01 | 2022-02-16 | 2021-06-30 | 3120000 | 1418000 | 4705550.28 | 1702000 | 150.8189 | 1
[10 empty] | 2018-12-06 | 2100-01-01 | 2022-02-16 | 2021-06-30 | 80000 | 37000 | 4705550.28 | 43000 | 5881.9379 | 1
[10 empty] | 2020-05-14 | 2100-01-01 | 2100-01-01 | 2023-06-30 | 17500000 | 7956000 | 4705550.28 | 9544000 | 26.8889 | 1
| 6 | City of Fresno | City of Fresno | Southwest Fresno Community Connector | 7798000 | 100 | Purchase 6 long-range electric buses | CP079 | CONST | 2020-06-25 | 2020-12-16 | 2023-06-25 | 2023-06-25 | 7555000 | 3349000 | 0 | 4206000 | 0 | 1
[7 empty] | Supporting Infrastructure for Buses | CP079 | PS&E | 2020-06-25 | 2100-01-01 | 2022-06-30 | 2022-06-30 | 243000 | 107000 | 0 | 136000 | 0 | 1
| 7 | City of Los Angeles | City of Los Angeles | Los Angeles City: Leading the Transformation to Zero-Emission Electric Bus Transit Service | 36104000 | 100 | Network Integration | CP029 | CONST | 2018-08-16 | 2018-08-16 | 2022-10-01 | 2019-12-31 | 250000 | 0 | 0 | 250000 | 0 | 1
[7 empty] | Zero-Emission Electric Buses, Supporting Infrastructure, and Facility Upgrades | CP029 | CONST | 2018-08-16 | 2019-10-25 | 2022-10-01 | 2019-12-31 | 35854000 | 16008000 | 0 | 19846000 | 0 | 1
| 8 | City of Santa Monica | City of Santa Monica | Electric Blue: Electrification of City of Santa Monica's Big Blue Bus | 3050000 | 100 | 10 Zero-Emission Electric Buses | CP054 | CONST | 2019-06-27 | 2020-02-03 | 2023-02-03 | 2023-02-03 | 3050000 | 1352000 | 0 | 1698000 | 0 | 1
| 9 | Livermore Amador Valley Transit Authority | Livermore Amador Valley Transit Authority | Dublin/Pleasanton Capacity Improvement and Congestion Reduction Program | 20500000 | 100 | Multi-level Parking Structure | CP051 | CONST | 2019-10-09 | 2020-12-08 | 2022-02-08 | 2022-11-30 | 20000000 | 9089000 | 0 | 10911000 | 0 | 1
[7 empty] | Network Integration | CP051 | CONST | 2018-12-06 | 2019-06-03 | 2021-12-31 | 2021-06-16 | 500000 | 0 | 157092.4 | 500000 | 31.4185 | 1
| 10 | Los Angeles County Metropolitan Transportation Authority | Los Angeles County Metropolitan Transportation Authority | Los Angeles Region Transit System Integration and Modernization Program of Projects | 1088499000 | 23.9963 | East San Fernando Valley Transit Corridor | CP030 | CONST | 2100-01-01 | 2022-12-31 | 2029-06-01 | 2100-01-01 | 0 | 0 | 0 | 0 |  | 1
[7 empty] | Gold Line Foothill Light Rail Extension Azusa to Pomona | CP030 | CONST | 2020-06-25 | 2019-08-14 | 2025-01-31 | 2100-01-01 | 249200000 | 111218000 | 0 | 137982000 | 0 | 1
[7 empty] | Gold Line Foothill Light Rail Extension Pomona to Montclair | CP030 | CONST | 2100-01-01 | 2025-12-31 | 2025-01-01 | 2100-01-01 | 0 | 0 | 0 | 0 |  | 1
[7 empty] | Green Line Light Rail Extension to Torrance | CP030 | CONST | 2100-01-01 | 2025-12-31 | 2031-06-30 | 2100-01-01 | 0 | 0 | 0 | 0 |  | 1
[7 empty] | Network Integration | CP030 | CONST | 2018-12-06 | 2020-02-27 | 2023-11-30 | 2100-01-01 | 7000000 | 0 | 0 | 7000000 | 0 | 1
[7 empty] | Orange/Red Line to Gold Line BRT Connector | CP030 | CONST | 2100-01-01 | 2023-12-31 | 2026-01-01 | 2100-01-01 | 0 | 0 | 0 | 0 |  | 1
[7 empty] | Vermont Transit Corridor | CP030 | PA&ED | 2021-03-13 | 2022-06-30 | 2029-06-01 | 2100-01-01 | 5000000 | 2231000 | 0 | 2769000 | 0 | 0
[7 empty] | West Santa Ana Light Rail Transit Corridor | CP030 | CONST | 2100-01-01 | 2024-12-31 | 2030-06-30 | 2100-01-01 | 0 | 0 | 0 | 0 |  | 1
| 11 | Los Angeles-San Diego-San Luis Obispo Rail Corridor Agency (LOSSAN) | Los Angeles-San Diego-San Luis Obispo Rail Corridor Agency (LOSSAN) | All Aboard 2018: Transforming SoCal Rail Travel | 22962000 | 111.3231 | Network Integration | CP031 | CONST | 2100-01-01 | 2021-12-01 | 2023-12-01 | 2100-01-01 | 0 | 0 | 0 | 0 |  | 1
[7 empty] | On-Time Performance Incentive Program for Service Improvements NCTD | CP031 | CONST | 2018-12-06 | 2019-02-01 | 2019-11-12 | 2021-12-05 | 2299000 | 1025000 | 2299000 | 1274000 | 100 | 1
[10 empty] | 2019-10-09 | 2019-02-01 | 2022-10-09 | 2022-10-09 | 4367000 | 1949000 | 4012067.29 | 2418000 | 91.8724 | 1
[10 empty] | 2020-10-22 | 2100-01-01 | 2023-10-22 | 2100-01-01 | 16296000 | 7333000 | 0 | 8963000 | 0 | 0
|  |  | North County Transit District (NCTD) | All Aboard 2018: Transforming SoCal Rail Travel | 22962000 | 111.3231 | North San Diego County Fencing | CP031 | CONST | 2020-01-30 | 2021-01-21 | 2024-01-21 | 2024-01-21 | 1241000 | 554000 | 11618.56 | 687000 | 0.93623 | 1
[9 empty] | PS&E | 2018-10-18 | 2100-01-01 | 2021-06-30 | 2021-06-30 | 259000 | 115000 | 58994.67 | 144000 | 22.7779 | 1
[7 empty] | OTC Pedestrian Crossing | CP031 | CONST | 2100-01-01 | 2100-01-01 | 2100-01-01 | 2100-01-01 | 0 | 0 | 0 | 0 |  | 1
[7 empty] | Signal Control Replacement - Carlsbad Crossings | CP031 | CONST | 2100-01-01 | 2100-01-01 | 2100-01-01 | 2100-01-01 | 0 | 0 | 0 | 0 |  | 1
[7 empty] | Signal Control Replacement - Encinitas & Del Mar | CP031 | CONST | 2100-01-01 | 2100-01-01 | 2100-01-01 | 2100-01-01 | 0 | 0 | 0 | 0 |  | 1
[7 empty] | Signal Control Replacement - Legacy Phase 2 | CP031 | CONST | 2100-01-01 | 2100-01-01 | 2100-01-01 | 2100-01-01 | 0 | 0 | 0 | 0 |  | 1
[7 empty] | Signal Control Replacement - San Diego Crossings | CP031 | CONST | 2100-01-01 | 2100-01-01 | 2100-01-01 | 2100-01-01 | 0 | 0 | 0 | 0 |  | 1
[7 empty] | Signal Train Control Replacement - Legacy Phase 1 | CP031 | CONST | 2021-06-25 | 2100-01-01 | 2100-01-01 | 2024-06-24 | 1100000 | 487000 | 0 | 613000 | 0 | 0
[7 empty] | Signal optimization: BNSF Junction Control Point | CP031 | CONST | 2100-01-01 | 2100-01-01 | 2100-01-01 | 2100-01-01 | 0 | 0 | 0 | 0 |  | 1
| 12 | Los Angeles-San Diego-San Luis Obispo Rail Corridor Agency (LOSSAN) | Los Angeles-San Diego-San Luis Obispo Rail Corridor Agency (LOSSAN) | Building Up: LOSSAN North Improvement Program | 91366000 | 66.5674 | Network Integration | CP031 | CONST | 2100-01-01 | 2021-12-01 | 2023-12-01 | 2100-01-01 | 0 | 0 | 0 | 0 |  | 1
[7 empty] | On-Time Performance Incentive Program for Service Improvements NCTD | CP031 | CONST | 2018-12-06 | 2019-02-01 | 2019-11-12 | 2021-12-05 | 2299000 | 1025000 | 2299000 | 1274000 | 100 | 1
[10 empty] | 2019-10-09 | 2019-02-01 | 2022-10-09 | 2022-10-09 | 4367000 | 1949000 | 4012067.29 | 2418000 | 91.8724 | 1
[10 empty] | 2020-10-22 | 2100-01-01 | 2023-10-22 | 2100-01-01 | 16296000 | 7333000 | 0 | 8963000 | 0 | 0
|  |  | North County Transit District (NCTD) | Building Up: LOSSAN North Improvement Program | 91366000 | 66.5674 | North San Diego County Fencing | CP031 | CONST | 2020-01-30 | 2021-01-21 | 2024-01-21 | 2024-01-21 | 1241000 | 554000 | 11618.56 | 687000 | 0.93623 | 1
[9 empty] | PS&E | 2018-10-18 | 2100-01-01 | 2021-06-30 | 2021-06-30 | 259000 | 115000 | 58994.67 | 144000 | 22.7779 | 1
[7 empty] | OTC Pedestrian Crossing | CP031 | CONST | 2100-01-01 | 2100-01-01 | 2100-01-01 | 2100-01-01 | 0 | 0 | 0 | 0 |  | 1
[7 empty] | Signal Control Replacement - Carlsbad Crossings | CP031 | CONST | 2100-01-01 | 2100-01-01 | 2100-01-01 | 2100-01-01 | 0 | 0 | 0 | 0 |  | 1
[7 empty] | Signal Control Replacement - Encinitas & Del Mar | CP031 | CONST | 2100-01-01 | 2100-01-01 | 2100-01-01 | 2100-01-01 | 0 | 0 | 0 | 0 |  | 1
[7 empty] | Signal Control Replacement - Legacy Phase 2 | CP031 | CONST | 2100-01-01 | 2100-01-01 | 2100-01-01 | 2100-01-01 | 0 | 0 | 0 | 0 |  | 1
[7 empty] | Signal Control Replacement - San Diego Crossings | CP031 | CONST | 2100-01-01 | 2100-01-01 | 2100-01-01 | 2100-01-01 | 0 | 0 | 0 | 0 |  | 1
[7 empty] | Signal Train Control Replacement - Legacy Phase 1 | CP031 | CONST | 2021-06-25 | 2100-01-01 | 2100-01-01 | 2024-06-24 | 1100000 | 487000 | 0 | 613000 | 0 | 0
[7 empty] | Signal optimization: BNSF Junction Control Point | CP031 | CONST | 2100-01-01 | 2100-01-01 | 2100-01-01 | 2100-01-01 | 0 | 0 | 0 | 0 |  | 1
| 13 | Peninsula Corridor Joint Powers Board | Peninsula Corridor Joint Powers Board | Peninsula Corridor Electrification Expansion Project | 203638000 | 61.7183 | Bike Parking Enhancements | CP039 | CONST | 2021-01-28 | 2022-01-28 | 2023-06-30 | 2023-08-12 | 2975000 | 1343000 | 0 | 1632000 | 0 | 0
[9 empty] | PS&E | 2021-01-28 | 2100-01-01 | 2021-01-29 | 2021-06-30 | 525000 | 237000 | 186423.28 | 288000 | 35.5092 | 0
[7 empty] | Corridor Wide Broadband Communications Network | CP039 | CONST | 2020-08-12 | 2100-01-01 | 2100-01-01 | 2100-01-01 | 1475000 | 666000 | 0 | 809000 | 0 | 0
[10 empty] | 2021-01-28 | 2100-01-01 | 2100-01-01 | 2100-01-01 | -1475000 | -666000 | 0 | -809000 | 0 | 0
[10 empty] | 2100-01-01 | 2100-01-01 | 2100-01-01 | 2100-01-01 | 0 | 0 | 0 | 0 |  | 1
[9 empty] | PS&E | 2018-10-18 | 2100-01-01 | 2021-04-30 | 2022-06-30 | 3000000 | 1354000 | 0 | 1646000 | 0 | 1
[10 empty] | 2020-08-12 | 2100-01-01 | 2100-01-01 | 2100-01-01 | -1475000 | -666000 | 0 | -809000 | 0 | 0
[10 empty] | 2021-01-28 | 2022-01-28 | 2021-04-30 | 2022-06-30 | 1000000 | 451000 | 0 | 549000 | 0 | 0
[11 empty] | 2100-01-01 | 2100-01-01 | 2100-01-01 | -525000 | -237000 | 0 | -288000 | 0 | 0
[7 empty] | Network Integration | CP039 | CONST | 2018-08-15 | 2018-10-10 | 2100-01-01 | 2020-09-30 | 3000000 | 0 | 2926950.8 | 3000000 | 97.565 | 1
[7 empty] | Procurement of 37 Electric Multiple Units (Multi-Year Funding) | CP039 | CONST | 2018-08-15 | 2024-12-31 | 2028-06-01 | 2100-01-01 | 31000000 | 14000000 | 0 | 17000000 | 0 | 1
[10 empty] | 2019-06-27 | 2018-12-14 | 2022-11-30 | 2024-12-31 | 27000000 | 12195000 | 56327786 | 14805000 | 208.6214 | 1
[10 empty] | 2020-08-12 | 2018-12-14 | 2022-11-30 | 2024-12-31 | 59182000 | 26732000 | 0 | 32450000 | 0 | 0
[10 empty] | 2100-01-01 | 2100-01-01 | 2100-01-01 | 2100-01-01 | 0 | 0 | 0 | 0 |  | 1
| 14 | Sacramento Regional Transit District | Sacramento Regional Transit District | Accelerating Rail Modernization and Expansion in the Capital Region | 64350000 | 82.6449 | Network Integration | CP053 | CONST | 2019-06-27 | 2019-06-27 | 2022-06-27 | 2021-11-30 | 250000 | 0 | 0 | 250000 | 0 | 1
[7 empty] | Purchase 20 Replacement and Expansion Low Floor LRVs | CP053 | CONST | 2019-12-05 | 2020-03-31 | 2026-02-12 | 2021-11-30 | 30932000 | 13768000 | 0 | 17164000 | 0 | 1
[10 empty] | 2021-08-19 | 2100-01-01 | 2100-01-01 | 2100-01-01 | 22000000 | 12208000 | 0 | 9792000 | 0 | 0
| 15 | San Bernardino County Transportation Authority (SBCTA) | San Bernardino County Transportation Authority (SBCTA) | Diesel Multiple Unit Vehicle to Zero- or Low-Emission Vehicle Conversion and West Valley Connector Bus Rapid Transit | 30000000 | 95 | DMU to ZMU Conversion (Design) | CP034 | PS&E | 2019-12-05 | 2100-01-01 | 2021-06-30 | 2021-06-30 | 4500000 | 1995000 | 1742773.01 | 2505000 | 38.7283 | 1
[7 empty] | Supporting Infrastructure for Zero-Emission Vehicles | CP034 | PA&ED | 2018-08-16 | 2100-01-01 | 2021-06-30 | 2021-06-30 | 500000 | 221000 | 243169.05 | 279000 | 48.6338 | 1
[7 empty] | ZEMU Supporting Infrastructure | CP034 | CONST | 2100-01-01 | 2100-01-01 | 2100-01-01 | 2100-01-01 | 0 | 0 | 0 | 0 |  | 1
[7 empty] | ZEMU Vehicle Procurement | CP034 | CONST | 2018-08-16 | 2019-11-13 | 2022-11-13 | 2024-06-01 | 12000000 | 5320000 | 9185571.96 | 6680000 | 76.5464 | 1
[10 empty] | 2019-12-05 | 2019-11-13 | 2022-11-13 | 2024-06-01 | 11500000 | 5099000 | 9185571.96 | 6401000 | 79.8745 | 1
| 16 | San Diego Association of Governments (SANDAG) | San Diego Association of Governments (SANDAG) | Ride Between the Line: Enhancing Access to Transit in San Diego | 5763000 | 0 | Improvements to transit stops for improved services including separated bike lane along University Avenue | CP077 | CONST | 2100-01-01 | 2022-12-31 | 2025-06-01 | 2100-01-01 | 0 | 0 | 0 | 0 |  | 1
| 17 | San Diego Metropolitan Transit System (MTS) | San Diego Metropolitan Transit System (MTS) | Blue Line Rail Corridor Transit Enhancements | 40098000 | 82.0041 | American Plaza Pedestrian Enhancements | CP032 | CONST | 2100-01-01 | 2100-01-01 | 2100-01-01 | 2100-01-01 | 0 | 0 | 0 | 0 |  | 1
[9 empty] | PS&E | 2019-03-14 | 2100-01-01 | 2021-06-30 | 2021-06-30 | 320000 | 142000 | 0 | 178000 | 0 | 1
[7 empty] | Beech Street Double Crossover | CP032 | CONST | 2020-12-03 | 2021-01-13 | 2024-01-13 | 2024-01-13 | 3691000 | 1646000 | 0 | 2045000 | 0 | 0
[9 empty] | PS&E | 2019-03-14 | 2100-01-01 | 2021-06-30 | 2021-06-30 | 360000 | 160000 | 0 | 200000 | 0 | 1
[7 empty] | Blue Line Feeder Bus Service (11 Buses) for Route 925 | CP032 | CONST | 2021-06-24 | 2100-01-01 | 2100-01-01 | 2021-06-24 | 13316000 | 5941000 | 0 | 7375000 | 0 | 0
[7 empty] | Blue Line Feeder Bus Service Charging Infrastructure for Route 925 | CP032 | CONST | 2100-01-01 | 2100-01-01 | 2100-01-01 | 2100-01-01 | 0 | 0 | 0 | 0 |  | 1
[9 empty] | PS&E | 2020-03-26 | 2100-01-01 | 2022-06-30 | 2100-01-01 | 372000 | 165000 | 0 | 207000 | 0 | 1
[7 empty] | Blue Line Feeder Bus Service Stop Improvements | CP032 | CONST | 2100-01-01 | 2100-01-01 | 2100-01-01 | 2100-01-01 | 0 | 0 | 0 | 0 |  | 1
[9 empty] | PS&E | 2019-03-14 | 2100-01-01 | 2021-06-30 | 2021-06-30 | 240000 | 107000 | 0 | 133000 | 0 | 1
[7 empty] | Green Line IMT Double Tracking | CP032 | CONST | 2020-12-03 | 2100-01-01 | 2024-12-31 | 2021-12-03 | 6354000 | 2835000 | 0 | 3519000 | 0 | 0
[9 empty] | PS&E | 2019-03-14 | 2100-01-01 | 2021-06-30 | 2021-06-30 | 635000 | 283000 | 0 | 352000 | 0 | 1
[7 empty] | Middletown Double Crossover | CP032 | CONST | 2019-10-09 | 2019-12-27 | 2022-12-27 | 2022-12-27 | 4977000 | 2220000 | 0 | 2757000 | 0 | 1
[7 empty] | Network Integration | CP032 | CONST | 2019-01-31 | 2019-06-13 | 2020-01-31 | 2020-01-31 | 250000 | 0 | 0 | 250000 | 0 | 1
[7 empty] | Old Town Transit Center Enhancements | CP032 | CONST | 2019-12-05 | 2020-08-11 | 2023-08-11 | 2023-08-11 | 2367000 | 1056000 | 0 | 1311000 | 0 | 1
| 18 | San Francisco Municipal Transportation Agency | San Francisco Municipal Transportation Agency | Transit Capacity Expansion Program | 26867000 | 100 | Procurement of 8 Additional Expansion Light Rail Vehicles | CP006 | CONST | 2018-08-15 | 2015-01-01 | 2021-08-16 | 2100-01-01 | 26867000 | 11912000 | 0 | 14955000 | 0 | 1
| 19 | San Joaquin Joint Powers Authority and San Joaquin Regional Rail Commission | San Joaquin Regional Rail Commission | Valley Rail | 500500000 | 13.1508 | Acquisition of Right of Way | CP035 | R/W | 2021-01-28 | 2100-01-01 | 2023-07-01 | 2100-01-01 | 9599000 | 4264000 | 0 | 5335000 | 0 | 0
[10 empty] | 2021-03-25 | 2100-01-01 | 2100-01-01 | 2100-01-01 | 4230000 | 1879000 | 0 | 2351000 | 0 | 0
[10 empty] | 2100-01-01 | 2100-01-01 | 2024-06-30 | 2100-01-01 | 0 | 0 | 0 | 0 |  | 1
[7 empty] | Coach Car Procurement (4 + 8 Matching) | CP035 | CONST | 2019-10-09 | 2020-05-04 | 2023-05-04 | 2100-01-01 | 15500000 | 6886000 | 0 | 8614000 | 0 | 1
[7 empty] | Design for BNSF Track Improvements | CP035 | CONST | 2021-03-25 | 2100-01-01 | 2100-01-01 | 2100-01-01 | 18250000 | 8108000 | 0 | 10142000 | 0 | 0
[9 empty] | PA&ED | 2021-03-25 | 2100-01-01 | 2100-01-01 | 2100-01-01 | 1750000 | 777000 | 0 | 973000 | 0 | 0
[9 empty] | PS&E | 2020-05-14 | 2100-01-01 | 2021-06-30 | 2100-01-01 | 450000 | 199000 | 0 | 251000 | 0 | 1
[12 empty] | 2100-01-01 | 2100-01-01 | -450000 | -199000 | 0 | -251000 | 0 | 1
[7 empty] | Environmental Clearance and Preliminary Engineering for Multiple Stations | CP035 | PA&ED | 2018-10-18 | 2100-01-01 | 2021-06-30 | 2100-01-01 | 12699000 | 5643000 | 20000000 | 7056000 | 157.4927 | 1
[10 empty] | 2021-01-28 | 2100-01-01 | 2021-06-30 | 2100-01-01 | -7699000 | -3337000 | 0 | -4362000 | 0 | 0
[7 empty] | Final Design | CP035 | PS&E | 2021-01-28 | 2100-01-01 | 2021-06-30 | 2100-01-01 | 7913000 | 3515000 | 0 | 4398000 | 0 | 0
[10 empty] | 2021-03-25 | 2100-01-01 | 2021-06-30 | 2100-01-01 | 1952000 | 867000 | 0 | 1085000 | 0 | 0
[10 empty] | 2100-01-01 | 2100-01-01 | 2021-06-30 | 2100-01-01 | 0 | 0 | 0 | 0 |  | 1
[7 empty] | Final Design (Oakley Station) | CP035 | PS&E | 2018-10-18 | 2100-01-01 | 2021-06-30 | 2100-01-01 | 626000 | 278000 | 0 | 348000 | 0 | 1
[7 empty] | Network Integration | CP035 | CONST | 2018-10-18 | 2100-01-01 | 2021-12-01 | 2100-01-01 | 1000000 | 0 | 666350.46 | 1000000 | 66.635 | 1
[7 empty] | Procurement, Station Construction, Track Expansion, Layover Facilities and Improvements (Multi-Year Funding) | CP035 | CONST | 2100-01-01 | 2022-09-30 | 2025-09-30 | 2100-01-01 | 0 | 0 | 15500000 | 0 | inf | 1
| 21 | Santa Barbara County Association of Governments | Santa Barbara County Association of Governments | Coastal Express/Pacific Surfliner Peak Hour Service Expansion and Integration Project | 9600000 | 100 | Central Coast Regional Transit Facility | CP048 | R/W | 2020-06-25 | 2100-01-01 | 2022-06-25 | 2022-06-25 | 3800000 | 1684000 | 0 | 2116000 | 0 | 1
[7 empty] | Procurement of Zero-Emission Buses | CP048 | CONST | 2020-06-25 | 2021-06-24 | 2024-06-24 | 2024-06-30 | 4300000 | 1906000 | 0 | 2394000 | 0 | 1
[7 empty] | Transit Facility Improvements for New Fleet and Services | CP048 | CONST | 2020-06-25 | 2020-12-31 | 2024-06-30 | 2024-06-30 | 1200000 | 532000 | 0 | 668000 | 0 | 1
[9 empty] | PS&E | 2018-10-18 | 2100-01-01 | 2021-06-30 | 2021-06-30 | 300000 | 133000 | 0 | 167000 | 0 | 1
| 22 | Santa Barbara County Association of Governments | Santa Barbara County Association of Governments | Goleta Train Depot | 13009000 | 16.9114 | Electric Shuttles and Associated Charging Station Infrastructure | CP047 | CONST | 2019-10-09 | 2021-03-30 | 2024-03-30 | 2021-03-30 | 400000 | 180000 | 0 | 220000 | 0 | 1
[7 empty] | Network Integration | CP047 | CONST | 2018-10-18 | 2018-10-18 | 2021-12-30 | 2021-12-30 | 250000 | 0 | 125705.23 | 250000 | 50.2821 | 1
[7 empty] | PA&ED for anw Multi-Modal Facility Adjacent to Existing Amtrak Train Station | CP047 | PA&ED | 2018-10-18 | 2100-01-01 | 2021-06-30 | 2021-06-30 | 590000 | 266000 | 513117.4 | 324000 | 86.9691 | 1
[10 empty] | 2019-08-15 | 2100-01-01 | 2022-06-30 | 2022-06-30 | 960000 | 434000 | 0 | 526000 | 0 | 1
| 23 | Santa Clara Valley Transportation Authority | Santa Clara Valley Transportation Authority | VTA’s BART Silicon Valley Extension, Phase II | 730000000 | 0 | BART Rail Service Extension to San Jose (Multi-Year Funding) | CP057 | CONST | 2100-01-01 | 2022-12-31 | 2030-06-30 | 2100-01-01 | 0 | 0 | 0 | 0 |  | 1
[11 empty] | 2100-01-01 | 2030-06-30 | 2100-01-01 | 0 | 0 | 0 | 0 |  | 1
| 24 | Shasta Regional Transportation Agency | Shasta Regional Transportation Agency | North State Intercity Bus System | 0 | inf | Procurement of 7 Electric Coaches & Related Infrastructure | CP045 | CONST | 2018-10-18 | 2100-01-01 | 2026-01-01 | 2100-01-01 | 8641000 | 3831000 | 0 | 4810000 | 0 | 1
| 25 | Solano Transportation Authority | Solano Transportation Authority | Solano Regional Transit Improvements | 0 | inf | Capital Improvements for Improved Transit Service | CP046 | CONST | 2018-10-18 | 2018-11-15 | 2022-06-30 | 2100-01-01 | 5875000 | 2666000 | 2875000 | 3209000 | 48.9362 | 1
[7 empty] | Charging Vehicle Infrastructure | CP046 | PS&E | 2020-03-26 | 2100-01-01 | 2022-06-30 | 2100-01-01 | 2000000 | 907000 | 0 | 1093000 | 0 | 1
[7 empty] | Network Integration | CP046 | CONST | 2019-01-31 | 2019-10-08 | 2020-08-30 | 2100-01-01 | 250000 | 0 | 215500 | 250000 | 86.2 | 1
[7 empty] | Vehicle Procurement - Pilot | CP046 | CONST | 2021-05-13 | 2021-05-18 | 2100-01-01 | 2024-05-13 | 1100000 | 499000 | 0 | 601000 | 0 | 0
| 26 | Sonoma-Marin Area Rail Transit District | Sonoma-Marin Area Rail Transit District | SMART Larkspur to Windsor Corridor | 21000000 | 100 | Network Integration | CP041 | CONST | 2018-08-16 | 2018-09-19 | 2021-12-31 | 2022-12-01 | 1000000 | 0 | 170791.14 | 1000000 | 17.0791 | 1
[7 empty] | Rail Extension to Windsor and Larkspur | CP041 | CONST | 2018-08-16 | 2018-09-19 | 2021-12-31 | 2022-12-01 | 20000000 | 9311000 | 11747351.6 | 10689000 | 58.7368 | 1
| 27 | Southern California Regional Rail Authority | Los Angeles County Metropolitan Transportation Authority | Southern California Optimized Rail Expansion (SCORE) | 875708000 | 41.59 | LINK US | CP033 | PA&ED | 2018-10-18 | 2100-01-01 | 2021-12-31 | 2100-01-01 | 23021000 | 10325000 | 0 | 12696000 | 0 | 1
[9 empty] | PS&E | 2020-12-03 | 2100-01-01 | 2021-12-30 | 2100-01-01 | 67336000 | 29856000 | 0 | 37480000 | 0 | 0
[9 empty] | R/W | 2019-08-15 | 2100-01-01 | 2022-06-30 | 2100-01-01 | 68531000 | 30737000 | 0 | 37794000 | 0 | 1
[10 empty] | 2020-06-25 | 2100-01-01 | 2023-06-30 | 2100-01-01 | 68532000 | 30387000 | 0 | 38145000 | 0 | 1
[7 empty] | LINK US (Multi-Year Funding) | CP033 | CONST | 2100-01-01 | 2023-12-31 | 2027-12-31 | 2100-01-01 | 0 | 0 | 0 | 0 |  | 1
|  |  | Orange County Transportation Authority | Southern California Optimized Rail Expansion (SCORE) | 875708000 | 41.59 | Irvine Station Improvements | CP033 | PA&ED | 2021-06-24 | 2100-01-01 | 2100-01-01 | 2100-01-01 | 6330000 | 2839000 | 0 | 3491000 | 0 | 0
[7 empty] | Orange County Maintenance Facility, Ph 1a | CP033 | PA&ED | 2019-10-09 | 2100-01-01 | 2022-06-30 | 2100-01-01 | 4829000 | 2165000 | 0 | 2664000 | 0 | 1
|  |  | Southern California Regional Rail Authority | Southern California Optimized Rail Expansion (SCORE) | 875708000 | 41.59 | Burbank Junction Speed Improvements | CP033 | CONST | 2021-03-25 | 2100-01-01 | 2100-01-01 | 2100-01-01 | 16480000 | 7307000 | 0 | 9173000 | 0 | 0
[9 empty] | PS&E | 2021-01-28 | 2100-01-01 | 2100-01-01 | 2100-01-01 | 1092000 | 484000 | 0 | 608000 | 0 | 0
[7 empty] | Chatsworth Station Improvements | CP033 | CONST | 2021-03-25 | 2100-01-01 | 2100-01-01 | 2100-01-01 | 1500000 | 665000 | 0 | 835000 | 0 | 0
[9 empty] | R/W | 2021-01-28 | 2100-01-01 | 2100-01-01 | 2100-01-01 | 3585000 | 1589000 | 572.07 | 1996000 | 0.015957 | 0
[7 empty] | Construction Component for Wave 1B (Control Point Attwood to Katella) | CP033 | CONST | 2019-12-05 | 2100-01-01 | 2100-01-01 | 2100-01-01 | 500000 | 224000 | 80433.78 | 276000 | 16.0868 | 1
[10 empty] | 2021-01-28 | 2100-01-01 | 2100-01-01 | 2100-01-01 | 329000 | 145000 | 80433.78 | 184000 | 24.448 | 0
[10 empty] | 2100-01-01 | 2100-01-01 | 2100-01-01 | 2100-01-01 | 0 | 0 | 0 | 0 |  | 1
[9 empty] | R/W | 2100-01-01 | 2100-01-01 | 2100-01-01 | 2100-01-01 | 0 | 0 | 0 | 0 |  | 1
[7 empty] | Design for Service Improvements Wave 1 and Wave 2 on the SB, VC, OC and LA Trunk lines (Multi-Year Funding) | CP033 | PS&E | 2018-12-06 | 2100-01-01 | 2024-10-30 | 2100-01-01 | 29825000 | 13377000 | 9846466.27 | 16448000 | 33.0141 | 1
[10 empty] | 2100-01-01 | 2100-01-01 | 2100-01-01 | 2100-01-01 | 0 | 0 | 0 | 0 |  | 1
[7 empty] | El Monte Station Improvements | CP033 | PA&ED | 2021-01-28 | 2100-01-01 | 2100-01-01 | 2100-01-01 | 140000 | 62000 | 11506.73 | 78000 | 8.2191 | 0
[7 empty] | Environmental Assessment for Wave 1 and Wave 2 | CP033 | PA&ED | 2018-08-16 | 2100-01-01 | 2023-06-01 | 2100-01-01 | 6500000 | 2915000 | 5965815.46 | 3585000 | 91.7818 | 1
[7 empty] | Fleet and Facility Improvements, Ph 1 (Multi-Year Funding) | CP033 | CONST | 2018-12-06 | 2100-01-01 | 2100-01-01 | 2100-01-01 | 23160000 | 10387000 | 3560346.85 | 12773000 | 15.3728 | 1
[10 empty] | 2100-01-01 | 2100-01-01 | 2100-01-01 | 2100-01-01 | 0 | 0 | 0 | 0 |  | 1
[7 empty] | Fleet and Facility Improvements, Ph 2 | CP033 | CONST | 2100-01-01 | 2100-01-01 | 2100-01-01 | 2100-01-01 | 0 | 0 | 0 | 0 |  | 1
[7 empty] | LA to Fullerton Trunk Line, Track Improvements, for Wave 1A, Design/Build (Multi-Year Funding) | CP033 | CONST | 2018-12-06 | 2100-01-01 | 2100-01-01 | 2100-01-01 | 5200000 | 2332000 | 169541.03 | 2868000 | 3.2604 | 1
[10 empty] | 2100-01-01 | 2100-01-01 | 2100-01-01 | 2100-01-01 | 0 | 0 | 0 | 0 |  | 1
[7 empty] | Marengo Siding Improvements | CP033 | PS&E | 2021-03-25 | 2100-01-01 | 2100-01-01 | 2100-01-01 | 522000 | 231000 | 0 | 291000 | 0 | 0
[9 empty] | R/W | 2021-03-25 | 2100-01-01 | 2100-01-01 | 2100-01-01 | 354000 | 156000 | 0 | 198000 | 0 | 0
[7 empty] | Network Integration | CP033 | CONST | 2018-10-18 | 2020-09-30 | 2023-06-30 | 2100-01-01 | 10000000 | 0 | 3870225.46 | 10000000 | 38.7023 | 1
[7 empty] | Rail Yard Rehabilitation & Modernization (Throat Segment) | CP033 | CONST | 2020-03-26 | 2021-06-30 | 2027-12-31 | 2100-01-01 | 19766000 | 8865000 | 157969.2 | 10901000 | 0.7992 | 1
[7 empty] | Serra Siding Extension | CP033 | PA&ED | 2021-01-28 | 2100-01-01 | 2100-01-01 | 2100-01-01 | 118000 | 52000 | 4842.1 | 66000 | 4.1035 | 0
[7 empty] | Signal Respacing Burbank to LA | CP033 | CONST | 2021-03-25 | 2100-01-01 | 2100-01-01 | 2100-01-01 | 6557000 | 2907000 | 0 | 3650000 | 0 | 0
[7 empty] | WAVE 2: Siding, Station Improvements, Signals and Capacity Improvements | CP033 | CONST | 2100-01-01 | 2100-01-01 | 2100-01-01 | 2100-01-01 | 0 | 0 | 0 | 0 |  | 1
| 28 | Transportation Agency for Monterey County | Transportation Agency for Monterey County | Rail Extension to Monterey County | 10148000 | 4.9271 | Network Integration | 1155 | CONST | 2018-10-18 | 2019-04-24 | 2022-04-24 | 2100-01-01 | 500000 | 0 | 0 | 500000 | 0 | 1
[7 empty] | New Passenger Rail Service to Salinas | 1155 | CONST | 2100-01-01 | 2023-12-01 | 2026-12-01 | 2100-01-01 | 0 | 0 | 0 | 0 |  | 1
[7 empty] | Positive Train Control | 1155 | CONST | 2100-01-01 | 2023-12-01 | 2026-12-01 | 2100-01-01 | 0 | 0 | 0 | 0 |  | 1
2020 | 1 | Antelope Valley Transit Authority | Antelope Valley Transit Authority | Reaching the Most Transit-Vulnerable: AVTA's Zero Emission "Microtransit" & Bus Expansion Proposal | 6503000 | 100 | Network Integration | CP059 | CONST | 2020-08-12 | 2100-01-01 | 2023-08-12 | 2023-08-12 | 250000 | 0 | 0 | 250000 | 0 | 0
[7 empty] | Purchase of 11 Zero-Emission Vehicles and Supporting Infrastructure | CP059 | CONST | 2020-08-12 | 2100-01-01 | 2023-08-12 | 2023-08-12 | 6253000 | 3251000 | 0 | 3002000 | 0 | 0
| 2 | Bay Area Rapid Transit District | Bay Area Rapid Transit District | The Transbaby Corridor Core Capacity Program: Vehicle Acquisition | 107100000 | 0 | Acquisition of 34 rail vehicles to support service capacity | CP060 | CONST | 2100-01-01 | 2100-01-01 | 2100-01-01 | 2100-01-01 | 0 | 0 | 0 | 0 |  | 1
| 3 | Capitol Corridor Joint Powers Authority | Capitol Corridor Joint Powers Authority | Sacramento Valley Station (SVS) Transit Center | 3914000 | 18.3955 | Network Integration | CP061 | CONST | 2020-08-12 | 2020-12-01 | 2022-02-28 | 2023-08-12 | 720000 | 0 | 0 | 720000 | 0 | 0
[7 empty] | New Northside station access | CP061 | CONST | 2021-12-31 | 2022-06-30 | 2025-06-30 | 2100-01-01 | 0 | 0 | 0 | 0 |  | 0
| 4 | City of Inglewood | City of Inglewood | Inglewood Transit Connector Project | 95200000 | 21.0084 | Automated People Mover | CP062 | CONST | 2022-12-31 | 2023-12-31 | 2026-11-01 | 2100-01-01 | 0 | 0 | 0 | 0 |  | 0
[9 empty] | PA&ED | 2020-08-13 | 2100-01-01 | 2023-06-30 | 2023-06-30 | 20000000 | 10000000 | 1823462.51 | 10000000 | 9.1173 | 0
| 5 | Lake Transit Authority | Lake Transit Authority | North State Intercity Bus System | 12994000 | 1.924 | New transit center, 4 new EV buses, expanded service routes, new infrastructure at maintenance facility | CP063 | PA&ED | 2020-12-31 | 2100-01-01 | 2026-01-31 | 2023-06-30 | 250000 | 125000 | 0 | 125000 | 0 | 0
| 6 | Long Beach Transit | Long Beach Transit | LBT/UCLA Electric Commuter Express | 6451000 | 100 | Purchase 5 zero-emission battery electric coaches | CP064 | CONST | 2021-05-13 | 2022-12-31 | 2025-12-01 | 2024-05-13 | 6451000 | 3225000 | 0 | 3226000 | 0 | 0
| 7 | Los Angeles County Metropolitan Transportation Authority and Southern California Regional Rail Authority | Los Angeles County Metropolitan Transportation Authority | Metrolink Antelope Valley Line Capital and Service Improvements | 107050000 | 0 | Balboa Double Track Extension/Lancaster Terminal Improvements | CP065 | CONST | 2025-12-31 | 2026-12-31 | 2027-06-01 | 2100-01-01 | 0 | 0 | 0 | 0 |  | 0
[9 empty] | R/W | 2023-12-31 | 2100-01-01 | 2027-12-31 | 2100-01-01 | 0 | 0 | 0 | 0 |  | 0
[7 empty] | Canyon Siding Extension/Brighton-McGinley Double Track | CP065 | CONST | 2025-12-31 | 2026-12-31 | 2027-06-01 | 2100-01-01 | 0 | 0 | 0 | 0 |  | 0
[9 empty] | R/W | 2022-12-31 | 2100-01-01 | 2026-12-31 | 2100-01-01 | 0 | 0 | 0 | 0 |  | 0
[7 empty] | Zero-Emission Multiple Units (Pilot) | CP065 | CONST | 2022-12-31 | 2023-12-31 | 2025-06-01 | 2100-01-01 | 0 | 0 | 0 | 0 |  | 0
| 8 | Los Angeles-San Diego-San Luis Obispo Rail Corridor Agency (LOSSAN) | Los Angeles-San Diego-San Luis Obispo Rail Corridor Agency (LOSSAN) | Building Up Control: LOSSAN Service Enhancement Program | 38743000 | 0 | Central Coast Layover Facility Expansion | CP066 | CONST | 2023-12-31 | 2024-12-31 | 2026-12-01 | 2100-01-01 | 0 | 0 | 0 | 0 |  | 0
[9 empty] | PS&E | 2021-12-31 | 2100-01-01 | 2025-12-31 | 2100-01-01 | 0 | 0 | 0 | 0 |  | 0
[7 empty] | San Diego County Maintenance and Layover Facility | CP066 | CONST | 2022-12-31 | 2023-12-31 | 2026-01-01 | 2100-01-01 | 0 | 0 | 0 | 0 |  | 0
[9 empty] | PA&ED | 2020-12-31 | 2100-01-01 | 2025-06-30 | 2100-01-01 | 0 | 0 | 0 | 0 |  | 0
[9 empty] | PS&E | 2021-12-31 | 2100-01-01 | 2025-12-31 | 2100-01-01 | 0 | 0 | 0 | 0 |  | 0
| 9 | Sacramento Regional Transit District | Sacramento Regional Transit District | Light Rail Modernization and Expansion of Low-Floor Fleet | 23600000 | 100 | Acquisition of light rail vehicles | CP067 | CONST | 2021-08-19 | 2100-01-01 | 2100-01-01 | 2100-01-01 | 23600000 | 11800000 | 0 | 11800000 | 0 | 0
| 10 | San Bernardino County Transportation Authority (SBCTA) and Omnitrans | San Bernardino County Transportation Authority (SBCTA) and Omnitrans | West Valley Connector Bus Rapid Transit Phase 1 & ZEB Initiative | 15000000 | 0 | Acquisition of zero-emission buses | CP068 | CONST | 2021-12-31 | 2022-12-31 | 2023-12-01 | 2100-01-01 | 0 | 0 | 0 | 0 |  | 0
| 11 | San Diego Association of Governments (SANDAG) | San Diego Association of Governments (SANDAG) | SDConnect: San Diego Rail Improvement Program | 12100000 | 37.1405 | Del Mar Bluffs Stabilization | CP069 | CONST | 2021-12-31 | 2022-12-31 | 2025-01-01 | 2100-01-01 | 0 | 0 | 0 | 0 |  | 0
[9 empty] | PS&E | 2020-08-13 | 2100-01-01 | 2023-06-30 | 2023-06-30 | 3774000 | 1887000 | 0 | 1887000 | 0 | 0
|  |  | San Diego Metropolitan Transit System (MTS) | SDConnect: San Diego Rail Improvement Program | 12100000 | 37.1405 | El Cajon Third Track | CP069 | CONST | 2021-12-31 | 2022-12-31 | 2023-06-01 | 2100-01-01 | 0 | 0 | 0 | 0 |  | 0
[9 empty] | PS&E | 2020-10-22 | 2100-01-01 | 2023-06-30 | 2023-06-30 | 720000 | 360000 | 0 | 360000 | 0 | 0
| 12 | San Francisco Municipal Transportation Agency | San Francisco Municipal Transportation Agency | Core Capacity Program | 41668000 | 0 | MUNI Forward J Line | CP070 | CONST | 2024-12-31 | 2025-12-31 | 2027-12-01 | 2100-01-01 | 0 | 0 | 0 | 0 |  | 0
[7 empty] | MUNI Forward M Line | CP070 | CONST | 2024-12-31 | 2025-12-31 | 2027-12-01 | 2100-01-01 | 0 | 0 | 0 | 0 |  | 0
| 13 | City of Santa Monica | City of Santa Monica | For People, Place and Planet: Connecting Inglewood to Regional Opportunities | 1105000 | 0 | Procurement of 7 zero-emission buses | CP071 | CONST | 2100-01-01 | 2022-06-30 | 2024-12-01 | 2100-01-01 | 0 | 0 | 0 | 0 |  | 1
| 14 | Solano Transportation Authority | Solano Transportation Authority | Solano Regional Transit Improvements Phase 2 | 10400000 | 27.8846 | Access Improvements at Fairfield Transit Center | CP072 | CONST | 2021-12-31 | 2022-12-31 | 2025-03-01 | 2100-01-01 | 0 | 0 | 0 | 0 |  | 0
[9 empty] | PS&E | 2021-05-13 | 2100-01-01 | 2025-06-30 | 2023-06-30 | 400000 | 200000 | 0 | 200000 | 0 | 0
[7 empty] | Access Improvements at Fairfield-Vacaville Stations | CP072 | CONST | 2021-12-31 | 2022-12-31 | 2025-01-01 | 2100-01-01 | 400000 | 200000 | 0 | 200000 | 0 | 0
[7 empty] | Access Improvements at Vacaville Transit Center | CP072 | CONST | 2021-12-31 | 2022-12-31 | 2025-01-01 | 2100-01-01 | 0 | 0 | 0 | 0 |  | 0
[7 empty] | Network Integration | CP072 | CONST | 2020-10-22 | 2022-06-30 | 2024-03-01 | 2100-01-01 | 1100000 | 0 | 0 | 1100000 | 0 | 0
[7 empty] | Shared Inductive Charging Infrastructure | CP072 | CONST | 2021-12-31 | 2022-12-31 | 2025-01-01 | 2100-01-01 | 0 | 0 | 0 | 0 |  | 0
[9 empty] | PS&E | 2020-10-22 | 2100-01-01 | 2025-06-30 | 2100-01-01 | 1000000 | 500000 | 0 | 500000 | 0 | 0
| 15 | Torrance Transit Department | Torrance Transit Department | Torrance Transit Bus Service Enhancement Program | 6000000 | 100 | Procurement of 7 zero-emission buses | CP073 | CONST | 2020-10-22 | 2021-03-01 | 2021-12-31 | 2100-01-01 | 6000000 | 3000000 | 0 | 3000000 | 0 | 0
| 16 | Transit Joint Powers Authority for Merced County | Transit Joint Powers Authority for Merced County | Improving Air Quality & Economic Growth with Electric Buses in Merced County, the Gateway to Yosemite | 3112000 | 100 | Procurement of 3 zero-emission buses | CP074 | CONST | 2020-10-22 | 2100-01-01 | 2026-01-31 | 2023-10-22 | 3112000 | 1556000 | 0 | 1556000 | 0 | 0
| 17 | San Francisco Bay Area Water Emergency Transportation Authority | San Francisco Bay Area Water Emergency Transportation Authority | Expansion of WETA Ferry Services | 9060000 | 0 | Acquisition of a new all-electric vessels and supporting infrastructure | CP075 | CONST | 2020-12-31 | 2021-06-01 | 2025-06-01 | 2100-01-01 | 0 | 0 | 0 | 0 |  | 0